IT Project Management Process Groups

According to the Project Management Institute PMBOK framework, project management consists of:

- Initiating

- Planning

- Executing

- Monitoring & Controlling

- Closing

For IT projects, Execution and Monitoring & Controlling consume most of the project effort and budget.

IT Project Execution Phase

- The Project Execution Phase is the stage in which the project team performs the work defined in the project management plan to produce the project's deliverables.

- It is the phase where plans are put into action and actual project work is carried out.

Example (IT Project)

Suppose a company is developing an Online Banking System.

- Planning Phase: Requirements, schedule, budget, and resources are planned.

- Execution Phase: Developers write code, testers test the application, infrastructure is configured, and the system is developed.

Objectives of Project Execution

- Produce project deliverables

- Manage project resources

- Implement approved changes

- Ensure quality standards

- Communicate with stakeholders

- Achieve project objectives

Inputs, Tools & Techniques, Outputs

| Inputs | Tools & Techniques | Outputs |
| --- | --- | --- |
| Project Management Plan | Expert Judgment | Deliverables |
| Project Documents | Project Management Information System (PMIS) | Work Performance Data |
| Approved Change Requests | Meetings | Issue Log Updates |
| Enterprise Environmental Factors | Interpersonal Skills | Change Requests |
| Organizational Process Assets | Leadership | Project Plan Updates |

Key Activities During Execution

Major Activities in Project Execution

1. Direct and Manage Project Work

Perform the tasks defined in the project plan.

Example

- Coding software modules

- Configuring servers

- Creating databases

2. Manage Project Team

Assign tasks and coordinate team members.

Example

- Assign developers to modules

- Conduct team meetings

- Resolve team conflicts

Manage Resources is the process of ensuring that project resources (people, equipment, materials, and facilities) are available, utilized effectively, and managed properly throughout the project.

In simple terms, it means leading, monitoring, motivating, and optimizing the use of project resources to achieve project objectives.

Purpose

The purpose of Manage Resources is to:

- Ensure resources are used efficiently

- Improve team performance

- Resolve conflicts

- Monitor resource utilization

- Enhance productivity

- Maintain a positive work environment

Example (IT Project)

Suppose a company is developing an E-Commerce Website.

Resources have already been acquired:

- 4 Developers

- 2 Testers

- 1 UI Designer

- Cloud Infrastructure

The Project Manager must now:

- Assign tasks

- Monitor workloads

- Resolve team conflicts

- Track performance

- Ensure resources are productive

These activities are part of Manage Resources.

Inputs, Tools & Techniques, Outputs (ITTO)

Inputs

| Input | Description |
| --- | --- |
| Project Management Plan | Defines how resources will be managed |
| Project Documents | Resource requirements, team assignments |
| Team Charter | Defines team values and working agreements |
| Issue Log | Resource-related issues |
| Enterprise Environmental Factors (EEF) | Organizational culture and policies |
| Organizational Process Assets (OPA) | Templates and lessons learned |

Example

The Resource Management Plan specifies:

- Reporting structure

- Roles and responsibilities

- Performance expectations

Tools & Techniques

1. Leadership

Guide and motivate team members.

Example

The Project Manager motivates developers to meet sprint goals.

2. Conflict Management

Resolve disagreements within the team.

Example

Two developers disagree on technology selection. The PM facilitates discussion and reaches a decision.

3. Problem Solving

Identify and resolve project issues.

Example

A server outage delays testing; the PM arranges alternative infrastructure.

4. Interpersonal and Team Skills

- Communication

- Negotiation

- Emotional Intelligence

- Influencing

Example

The PM negotiates resource sharing with another project manager.

5. Project Management Information System (PMIS)

Monitor resource utilization and performance.

Example

Using Jira, Azure DevOps, or MS Project to track assignments and progress.

Outputs

| Output | Description |
| --- | --- |
| Change Requests | Requests for resource changes |
| Project Management Plan Updates | Updates to resource plans |
| Project Documents Updates | Updated issue logs and assignments |
| Enterprise Environmental Factor Updates | Improved organizational knowledge |

Key Activities in Managing Resources

1. Assign and Coordinate Work

Ensure work is distributed appropriately.

Example

| Team Member | Task |
| --- | --- |
| Developer A | User Authentication |
| Developer B | Payment Gateway |
| Tester A | Functional Testing |

2. Monitor Resource Utilization

Track how resources are being used.

Example

A developer is overloaded while another has little work. The PM redistributes tasks.

3. Resolve Conflicts

Address disagreements quickly.

Example

Two teams need the same database server. The PM prioritizes usage and schedules access.

4. Motivate Team Members

Keep morale and engagement high.

Example

Recognizing a developer who successfully completed a critical module ahead of schedule.

5. Manage Team Performance

Evaluate productivity and identify improvement opportunities.

Example

Reviewing sprint velocity and code quality metrics.

6. Address Resource Issues

Handle absences, turnover, and skill gaps.

Example

A key developer resigns; the PM arranges knowledge transfer and replacement.

Example Scenario

Project

Hospital Management System

Acquired Resources

- 5 Developers

- 2 Testers

- 1 Business Analyst

- Cloud Environment

Resource Management Activities

- Conduct daily stand-up meetings

- Monitor workload distribution

- Resolve conflicts

- Track productivity

- Provide coaching and support

Outputs

- Improved collaboration

- Balanced workloads

- Higher productivity

- Reduced project delays

Common Resource Management Challenges

- Resource Overallocation

- One person assigned too many tasks.

- Resource Underutilization

- Resources remain idle.

- Team Conflicts

- Disagreements affect productivity.

- Skill Gaps

- Team lacks required expertise.

- Employee Turnover

- Key resources leave the project.

Difference Between Acquire Resources and Manage Resources

| Acquire Resources | Manage Resources |
| --- | --- |
| Obtain resources for the project | Utilize and control resources effectively |
| Focuses on staffing and procurement | Focuses on performance and productivity |
| Done when resources are needed | Continues throughout project execution |
| Example: Hiring developers | Example: Managing developers' workload |

Summary

| Aspect | Description |
| --- | --- |
| Process | Manage Resources |
| Process Group | Executing |
| Purpose | Ensure resources are used effectively and efficiently |
| Key Inputs | Resource Management Plan, Team Charter, Issue Log |
| Key Tools | Leadership, Conflict Management, Problem Solving, PMIS |
| Key Outputs | Change Requests, Plan Updates, Improved Team Performance |
| Example | Assigning work, monitoring workloads, resolving conflicts |

One-Line Definition

Manage Resources is the PMBOK process of leading, monitoring, and optimizing project resources to improve performance and successfully achieve project objectives.

3. Acquire Resources

Obtain required people, hardware, software, and services.

Example

- Hire a Java Developer

- Purchase cloud hosting services

Acquire Resources (PMBOK)

What is Acquire Resources?

Acquire Resources is the process of obtaining the team members, facilities, equipment, materials, and other resources needed to complete project work.

In simple terms, it means getting the right people and resources at the right time for the project.

Purpose

The purpose of Acquire Resources is to:

- Ensure the project has sufficient resources

- Assign qualified team members

- Obtain necessary hardware, software, and facilities

- Support project execution and delivery

Example (IT Project)

Suppose a company is developing a Hospital Management System.

The Project Manager identifies the need for:

- 4 Software Developers

- 2 Test Engineers

- 1 UI/UX Designer

- Cloud Server

- Software Licenses

The process of obtaining these resources is called Acquire Resources.

Inputs, Tools & Techniques, Outputs (ITTO)

Inputs

| Input | Description |
| --- | --- |
| Project Management Plan | Defines resource requirements |
| Project Documents | Resource needs, schedules, risk register |
| Enterprise Environmental Factors (EEF) | Organizational structure, labor market |
| Organizational Process Assets (OPA) | Policies, procedures, historical data |

Example

A project plan indicates:

- Need for 5 developers

- AWS cloud environment

- Database administrator

These become inputs for acquiring resources.

Tools & Techniques

1. Pre-assignment

Resources are assigned before the project starts.

Example

A client specifically requests a senior architect for the project.

2. Negotiation

Discuss resource allocation with managers or vendors.

Example

The Project Manager negotiates with the IT department to assign two experienced developers.

3. Acquisition

Acquire resources from outside the organization.

Example

Hiring a cybersecurity consultant on contract.

4. Virtual Teams

Use geographically distributed team members.

Example

Developers work from Nepal, India, and the USA on the same project.

5. Multi-Criteria Decision Analysis

Select resources based on multiple factors.

Example

Choosing a developer based on:

- Skills

- Experience

- Availability

- Cost

Outputs

| Output | Description |
| --- | --- |
| Physical Resource Assignments | Equipment, facilities, tools assigned |
| Project Team Assignments | Team members assigned |
| Resource Calendars | Availability schedules |
| Change Requests | Additional resources may be requested |
| Project Management Plan Updates | Resource plans updated |
| Project Documents Updates | Resource records updated |

Resource Acquisition Process

Step 1: Identify Resource Requirements

Determine what resources are needed.

Example

- 3 Java Developers

- 1 Tester

- 1 Business Analyst

Step 2: Check Resource Availability

Determine whether resources are available internally.

Example

The organization already has 2 Java Developers available.

Step 3: Acquire Remaining Resources

Hire or procure additional resources.

Example

Hire one additional Java Developer through a recruitment agency.

Step 4: Assign Resources

Allocate resources to project activities.

Example

- Developer A → User Management Module

- Developer B → Payment Module

- Tester → System Testing

Step 5: Update Resource Calendar

Record when resources are available.

Example

Developer A available from July 1 to December 31.

Example Scenario

Project

Online Banking System

Resource Requirements

| Resource | Quantity |
| --- | --- |
| Java Developer | 4 |
| Tester | 2 |
| DevOps Engineer | 1 |
| AWS Server | 2 |
| Database Administrator | 1 |

Activities

- Negotiate with department managers

- Hire contract developers

- Procure cloud servers

- Assign team members

Outputs

- Project team formed

- Servers provisioned

- Resource calendar updated

- Project work begins

Challenges in Acquiring Resources

- Resource Shortage

- Needed skills may not be available.

- Resource Conflicts

- The same person may be assigned to multiple projects.

- Budget Constraints

- Limited budget may restrict hiring.

- Skill Gaps

- Available resources may require training.

Summary

| Aspect | Description |
| --- | --- |
| Process | Acquire Resources |
| Process Group | Executing |
| Purpose | Obtain people, equipment, facilities, and materials needed for the project |
| Key Inputs | Project Management Plan, Project Documents, EEF, OPA |
| Key Tools | Pre-assignment, Negotiation, Acquisition, Virtual Teams |
| Key Outputs | Team Assignments, Resource Calendars, Resource Assignments |
| Example | Hiring developers, assigning testers, procuring cloud servers |

One-Line Definition

Acquire Resources is the PMBOK process of obtaining and assigning the people, equipment, facilities, and materials required to successfully execute a project.

4. Develop Team

Improve team skills through training and coaching.

Example

- Agile training

- AI certification programs

- Technical workshops

Team Development Stages (Tuckman's Model)

Bruce Tuckman proposed that teams typically go through five stages of development:

- Forming

- Storming

- Norming

- Performing

- Adjourning

Understanding these stages helps project managers build effective teams and resolve issues.

1. Forming Stage

What Happens?

The team is newly created. Members are getting to know each other and understanding the project's goals, roles, and expectations.

Characteristics

- Excitement and enthusiasm

- Uncertainty about responsibilities

- Dependence on the project manager

- Polite interactions

Project Manager's Role

- Provide clear direction

- Explain project objectives

- Define roles and responsibilities

Example

A company starts a mobile banking application project. Developers, testers, business analysts, and UI designers meet for the first time. Team members introduce themselves and learn about the project.

2. Storming Stage

What Happens?

Conflicts and disagreements begin to appear as team members express different opinions and working styles.

Characteristics

- Arguments and disagreements

- Competition among members

- Resistance to authority or processes

- Frustration and tension

Project Manager's Role

- Resolve conflicts

- Encourage communication

- Clarify expectations

- Build trust

Example

A developer wants to use React while another prefers Angular. Testers complain that requirements are unclear. Team members disagree on technical approaches.

3. Norming Stage

What Happens?

The team starts working together effectively. Members understand their roles and establish common working practices.

Characteristics

- Improved cooperation

- Better communication

- Mutual trust develops

- Team rules are accepted

Project Manager's Role

- Encourage collaboration

- Support teamwork

- Recognize achievements

Example

The team agrees on coding standards, sprint ceremonies, communication channels, and issue-tracking processes. Members begin helping each other solve problems.

4. Performing Stage

What Happens?

The team reaches peak productivity and works efficiently toward project goals.

Characteristics

- High trust and collaboration

- Minimal supervision required

- Strong problem-solving ability

- High productivity

Project Manager's Role

- Empower the team

- Remove obstacles

- Focus on strategic issues

Example

The Agile team delivers features every sprint, resolves issues quickly, and consistently meets deadlines with high-quality output.

5. Adjourning Stage

What Happens?

The project is completed, and the team is disbanded or reassigned.

Characteristics

- Project closure activities

- Knowledge transfer

- Celebration of success

- Team members move to new projects

Project Manager's Role

- Conduct lessons learned

- Recognize contributions

- Ensure proper project closure

Example

After successfully launching the banking application, the team conducts a project review meeting, documents lessons learned, and members move to different projects.

Summary Table

| Stage | Key Characteristics | Project Manager's Focus |
| --- | --- | --- |
| Forming | Team members meet and learn about project | Provide direction and clarity |
| Storming | Conflicts and disagreements arise | Resolve conflicts and build trust |
| Norming | Team develops cooperation and standards | Encourage collaboration |
| Performing | High productivity and independence | Empower team and remove obstacles |
| Adjourning | Project completion and team dissolution | Close project and capture lessons learned |

Simple Example

Imagine a team developing an e-commerce website:

- Forming: Team members meet and discuss project goals.

- Storming: Disagreements occur about technology choices.

- Norming: Team agrees on processes and standards.

- Performing: Team delivers features efficiently and meets deadlines.

- Adjourning: Website launches successfully, and the team is released.

Memory Tip:
F → S → N → P → A
Forming → Storming → Norming → Performing → Adjourning
"First Some New Projects Arrive" can help you remember the sequence

5. Manage Communications

Share project information with stakeholders.

Example

- Weekly status reports

- Sprint review meetings

- Client demonstrations

6. Manage Quality

Ensure deliverables meet quality standards.

Example

- Code reviews

- Unit testing

- Security testing

7. Manage Stakeholder Engagement

Maintain stakeholder involvement and satisfaction.

Example

- Gather user feedback

- Conduct product demonstrations

Inputs, Tools & Techniques, Outputs (ITTO)

Inputs

Inputs are resources and information needed to start execution.

| Input | Description |
| --- | --- |
| Project Management Plan | Approved roadmap for execution |
| Project Documents | Requirements, schedules, risk register, etc. |
| Approved Change Requests | Changes authorized for implementation |
| Enterprise Environmental Factors (EEF) | Organizational culture, tools, infrastructure |
| Organizational Process Assets (OPA) | Templates, guidelines, lessons learned |

Example

For an ERP implementation project:

- Project Plan specifies 6-month schedule.

- Risk Register identifies data migration risks.

- Approved Change Request adds a reporting module.

Tools & Techniques

| Tool/Technique | Purpose |
| --- | --- |
| Expert Judgment | Obtain guidance from specialists |
| Meetings | Coordinate work and decisions |
| Project Management Information System (PMIS) | Track project activities |
| Leadership Skills | Guide team performance |
| Communication Skills | Share project information |
| Conflict Management | Resolve team issues |

Example

A Project Manager conducts:

- Daily Scrum meetings

- Weekly status reviews

- Risk review meetings

Outputs

Outputs are the results produced during execution.

| Output | Description |
| --- | --- |
| Deliverables | Products or services created |
| Work Performance Data | Raw performance information |
| Issue Log Updates | Newly identified issues |
| Change Requests | Requests for modifications |
| Project Plan Updates | Revisions to project plans |
| Project Document Updates | Updated project records |

Example: IT Project Execution

Project

Online Shopping Application

Inputs

- Approved Project Plan

- Requirement Specification

- Budget: $100,000

- Development Team

Activities

- Design user interface

- Develop application

- Perform testing

- Conduct review meetings

- Manage team members

Outputs

- Working e-commerce application

- Test reports

- Progress reports

- Change requests

- Updated project documents

Monitoring & Controlling Phase

Purpose

Track project performance and compare actual results against planned results.

Questions answered:

- Are we on schedule?

- Are we within budget?

- Are risks increasing?

- Is quality acceptable?

- Do changes need approval?

Inputs, Tools & Techniques, Outputs

| Inputs | Tools & Techniques | Outputs |
| --- | --- | --- |
| Project Management Plan | Variance Analysis | Work Performance Reports |
| Work Performance Data | Trend Analysis | Change Requests |
| Project Documents | Earned Value Management | Forecasts |
| Agreements | Root Cause Analysis | Corrective Actions |
| Enterprise Environmental Factors | Meetings | Updated Project Documents |

Major Monitoring Activities

Schedule Monitoring

Compare:

- Planned progress

- Actual progress

Example:

Planned completion = 60%

Actual completion = 45%

Schedule variance exists.

Cost Monitoring

Compare:

- Budgeted cost

- Actual cost

Example:

Budget = $100,000

Actual spent = $120,000

Cost overrun = $20,000

Quality Monitoring

Check:

- Defect rates

- Test coverage

- User acceptance results

Risk Monitoring

Track:

- Open risks

- New risks

- Risk response effectiveness

Team Management in IT Projects

Functional Team

People belong to departments.

Example:

- Development Department

- Testing Department

- Infrastructure Department

Advantages:

- Technical expertise

Disadvantages:

- Slow communication

Matrix Team

Employees report to:

- Functional Manager

- Project Manager

Types:

Weak Matrix

Functional manager has more authority.

Balanced Matrix

Authority shared.

Strong Matrix

Project manager has more authority.

Projectized Team

Resources dedicated entirely to project.

Advantages:

- Faster decisions

- Better coordination

Disadvantages:

- Resource duplication

Agile / Cross-functional Team

Common in modern IT projects.

Includes:

- Developers

- Testers

- UX Designers

- Business Analysts

- DevOps Engineers

Advantages:

- Fast delivery

- Better collaboration

Tracking Project Progress

A. Earned Value Management (EVM)

Measures:

- Scope

- Schedule

- Cost

Together.

Key Metrics

Planned Value (PV)

Budgeted value of work planned.

Example:

Planned work = $50,000

PV = $50,000

Earned Value (EV)

Budgeted value of work completed.

Example:

40% complete of $100,000 project

EV = $40,000

Actual Cost (AC)

Actual money spent.

Example:

AC = $45,000

Schedule Variance (SV)

SV = EV − PV

Example:

40,000 − 50,000

SV = -10,000

Project is behind schedule.

Cost Variance (CV)

CV = EV − AC

40,000 − 45,000

CV = -5,000

Project is over budget.

Schedule Performance Index (SPI)

SPI = EV / PV

40,000 / 50,000 = 0.8

SPI < 1 → Behind Schedule

Cost Performance Index (CPI)

CPI = EV / AC

40,000 / 45,000 = 0.89

CPI < 1 → Over Budget

EVM Interpretation

EVM performance interpretation

Quick interpretation of common EVM indicators.

00.81.62.43.2SPI < 1SPI = 1SPI > 1CPI < 1CPI = 1CPI > 1

- SPI < 1 = Behind Schedule

- SPI > 1 = Ahead of Schedule

- CPI < 1 = Over Budget

- CPI > 1 = Under Budget

B. Burn Down Chart

Used in Agile projects.

Tracks:

- Remaining work

- Time remaining

Example:

| Sprint Day | Remaining Story Points |
| --- | --- |
| Day 1 | 100 |
| Day 3 | 75 |
| Day 5 | 55 |
| Day 8 | 30 |
| Day 10 | 0 |

Benefits:

- Shows sprint progress

- Predicts completion

- Identifies delays early

C. Velocity

Measures completed story points per sprint.

Example:

| Sprint | Velocity |
| --- | --- |
| Sprint 1 | 25 |
| Sprint 2 | 30 |
| Sprint 3 | 28 |

Average Velocity = 28

Used for release planning.

D. Throughput

Number of completed work items per period.

Example:

- Week 1 = 12 tickets

- Week 2 = 15 tickets

Useful in Kanban environments.

E. Cycle Time

Time from work start to completion.

Example:

Task started: June 1

Completed: June 6

Cycle Time = 5 days

6. Controlling Project Progress

Purpose:

Take corrective action when project deviates from plan.

Control Techniques

Corrective Action

Fix current issue.

Example:

Add developers to recover schedule.

Preventive Action

Avoid future issue.

Example:

Increase automated testing.

Defect Repair

Fix identified defects.

Example:

Bug fixing before release.

Replanning

Update baseline when approved.

Example:

New feature added.

Schedule revised.

7. Change Management

Definition

Formal process used to evaluate, approve, reject, and implement project changes.

Without change control:

- Scope creep

- Budget overrun

- Schedule delays

occur frequently.

8. Change Management Process

Step 1: Raise Change Request

Example:

Client requests AI-powered chatbot feature.

Step 2: Log Change Request

Record:

- Description

- Requestor

- Date

- Priority

Step 3: Impact Analysis

Analyze impact on:

- Scope

- Cost

- Schedule

- Resources

- Risks

- Quality

Example:

Additional effort = 120 hours

Cost increase = $8,000

Schedule impact = 2 weeks

Step 4: Review by Change Control Board (CCB)

CCB evaluates:

- Business value

- Risk

- Cost-benefit

Step 5: Decision

- Approved

- Rejected

- Deferred

Step 6: Update Baselines

If approved:

- Scope baseline

- Schedule baseline

- Cost baseline

are updated.

Step 7: Implement Change

Development team executes change.

Step 8: Verify and Close

Confirm:

- Change implemented

- Requirements satisfied

- Documentation updated

Conflict Management in Project Management

What is Conflict?

A conflict is a disagreement or difference of opinion between individuals or groups regarding goals, priorities, resources, processes, or solutions.

Example

In an IT project:

- Developer A wants to use React.

- Developer B wants to use Angular.

This disagreement is a conflict.

Is Conflict Always Wrong?

No.

PMBOK recognizes that conflict can be positive (constructive) or negative (destructive).

Positive Conflict

Leads to:

- Better ideas

- Innovation

- Problem solving

- Improved decisions

Example

Two architects debate different database designs. After discussion, they choose a more scalable solution.

Negative Conflict

Leads to:

- Delays

- Poor morale

- Reduced productivity

- Team divisions

Example

Team members stop communicating because of personal disagreements.

Why Does Conflict Need to Be Managed?

Conflicts are natural in projects because:

- Resources are limited

- Deadlines are tight

- Team members have different skills and backgrounds

- Stakeholders have competing priorities

If conflicts are not managed:

- Productivity decreases

- Team morale suffers

- Project delays occur

- Quality declines

The goal is not to eliminate conflict, but to manage it constructively.

Conflict Management Approaches (PMBOK)

1. Collaborating (Problem Solving / Win-Win)

Definition

Both parties work together to find a solution that satisfies everyone.

Characteristics

- Addresses root cause

- High cooperation

- Long-term solution

- Best technique when time permits

Example

Developer A wants React.

Developer B wants Angular.

The team evaluates:

- Skills

- Project requirements

- Performance

- Support

After analysis, they choose the best technology for the project.

Result

✔ Both parties feel heard.

✔ Best solution found.

When to Use

- Important issue

- Long-term relationships matter

- Time available for discussion

2. Compromising (Give and Take)

Definition

Each party gives up something to reach a mutually acceptable solution.

Characteristics

- Moderate satisfaction

- Quick resolution

- Temporary solution

Example

Two departments need the same server.

Agreement:

- Team A uses it in the morning.

- Team B uses it in the afternoon.

Result

✔ Both gain something.

✖ Neither gets everything.

When to Use

- Limited time

- Equal power among parties

- Temporary solution needed

3. Forcing (Directing / Win-Lose)

Definition

One party imposes a solution using authority or power.

Characteristics

- Fast decision

- One side wins

- Other side loses

- May create resentment

Example

A project is behind schedule.

The Project Manager decides:

"We will use React. Discussion closed."

Result

✔ Quick resolution.

✖ Team may feel ignored.

When to Use

- Emergency situations

- Safety or compliance issues

- Immediate action required

4. Avoiding (Withdraw / Retreat)

Definition

The conflict is postponed or ignored.

Characteristics

- No immediate resolution

- Useful for minor issues

- May allow emotions to cool down

Example

Two team members argue during a stressful release week.

The PM postpones the discussion until after deployment.

Result

✔ Immediate tension reduced.

✖ Problem remains unresolved.

When to Use

- Issue is minor

- More information is needed

- Better timing required

5. Smoothing (Accommodating)

Definition

Focus on areas of agreement while downplaying differences.

Characteristics

- Maintains harmony

- Preserves relationships

- Does not address root cause

Example

A developer and tester disagree about defect severity.

The PM says:

"We all want a successful release. Let's focus on that common goal."

The discussion is softened and the team moves forward.

Result

✔ Maintains good relationships.

✖ Root issue may still exist.

When to Use

- Relationship is more important than the issue

- Temporary harmony is needed

Comparison Table

| Approach | Outcome | Best For | Example |
| --- | --- | --- | --- |
| Collaborating | Win-Win | Important issues and long-term solutions | Jointly selecting the best technology |
| Compromising | Partial Win-Win | Quick agreement | Sharing a server between teams |
| Forcing | Win-Lose | Emergencies and urgent decisions | PM mandates a technology choice |
| Avoiding | No Immediate Resolution | Minor issues or cooling-off period | Postponing an argument until later |
| Smoothing | Harmony Maintained | Relationship preservation | Focusing on common project goals |

Example: Same Conflict, Different Approaches

Conflict: Developer A wants React; Developer B wants Angular.

| Approach | What Happens? |
| --- | --- |
| Collaborating | Analyze requirements and choose the best option together |
| Compromising | Use React for one module and Angular for another |
| Forcing | PM selects React and ends the discussion |
| Avoiding | Decision postponed until next week |
| Smoothing | PM emphasizes shared project goals and reduces tension |

Earned Value Management (EVM)

What is Earned Value Management?

Earned Value Management (EVM) is a project performance measurement technique that integrates:

- Scope

- Schedule

- Cost

to determine whether a project is progressing as planned.

It helps answer:

- Are we ahead or behind schedule?

- Are we under or over budget?

- How much work has actually been completed?

- What will the project likely cost when finished?

Basic EVM Metrics

Assume a project has:

- Total Budget (BAC) = $100,000

- Planned completion by today = 50%

- Actual completion by today = 40%

- Actual money spent = $45,000

1. Planned Value (PV)

Definition

The budgeted value of work that should have been completed by a certain date.

Formula

PV=Planned % Completion×BAC

Example

Planned completion = 50%

BAC = $100,000

PV=50%×100,000=$50,000

Interpretation: By today, the project was supposed to complete $50,000 worth of work.

2. Earned Value (EV)

Definition

The budgeted value of work actually completed.

Formula

EV=Actual % Completion×BAC

Example

Actual completion = 40%

BAC = $100,000

EV=40%×100,000=$40,000

Interpretation: The project has actually completed $40,000 worth of planned work.

3. Actual Cost (AC)

Definition

The actual money spent on the completed work.

Formula

AC=Actual Cost Incurred

Example

Actual spending = $45,000

AC=$45,000

Schedule Performance Formulas

4. Schedule Variance (SV)

Definition

Difference between earned work and planned work.

Formula

SV=EV-PV

Example

EV = $40,000

PV = $50,000

SV=40,000-50,000=-10,000

Interpretation

- SV > 0 → Ahead of schedule

- SV = 0 → On schedule

- SV < 0 → Behind schedule

Result:

SV = -$10,000

Project is behind schedule.

5. Schedule Performance Index (SPI)

Definition

Measures schedule efficiency.

Formula

SPI=EVPV

Example

SPI=40,00050,000
SPI=0.8

Interpretation

- SPI > 1 → Ahead of schedule

- SPI = 1 → On schedule

- SPI < 1 → Behind schedule

Result:

SPI = 0.8

The project earns only 80 cents of planned work for every $1 of scheduled work.

Cost Performance Formulas

6. Cost Variance (CV)

Definition

Difference between earned value and actual spending.

Formula

CV=EV-AC

Example

CV=40,000-45,000
CV=-5,000

Interpretation

- CV > 0 → Under budget

- CV = 0 → On budget

- CV < 0 → Over budget

Result:

CV = -$5,000

Project is over budget.

7. Cost Performance Index (CPI)

Definition

Measures cost efficiency.

Formula

CPI=EVAC

Example

CPI=40,00045,000
CPI=0.89

Interpretation

- CPI > 1 → Under budget

- CPI = 1 → On budget

- CPI < 1 → Over budget

Result:

CPI = 0.89

For every $1 spent, only $0.89 worth of work is earned.

Forecasting Formulas

8. Budget at Completion (BAC)

Definition

Total approved project budget.

Formula

BAC=Total Planned Budget

Example

BAC=$100,000

9. Estimate at Completion (EAC)

Definition

Expected total project cost when completed.

Common Formula

EAC=BACCPI

Example

EAC=100,0000.89
EAC=$112,360

Interpretation

The project is expected to finish at approximately $112,360.

10. Estimate to Complete (ETC)

Definition

Expected additional cost required to finish the remaining work.

Formula

ETC=EAC-AC

Example

ETC=112,360-45,000
ETC=$67,360

Interpretation

Need another $67,360 to complete the project.

11. Variance at Completion (VAC)

Definition

Expected budget surplus or deficit at project completion.

Formula

VAC=BAC-EAC

Example

VAC=100,000-112,360
VAC=-12,360

Interpretation

Project is expected to exceed budget by $12,360.

Complete Example Summary

Given:

- BAC = $100,000

- PV = $50,000

- EV = $40,000

- AC = $45,000

| Metric | Formula | Result | Meaning |
| --- | --- | --- | --- |
| PV | Planned % × BAC | $50,000 | Planned work |
| EV | Actual % × BAC | $40,000 | Earned work |
| AC | Actual cost | $45,000 | Money spent |
| SV | EV − PV | -$10,000 | Behind schedule |
| SPI | EV ÷ PV | 0.80 | Schedule inefficient |
| CV | EV − AC | -$5,000 | Over budget |
| CPI | EV ÷ AC | 0.89 | Cost inefficient |
| BAC | Total budget | $100,000 | Approved budget |
| EAC | BAC ÷ CPI | $112,360 | Expected final cost |
| ETC | EAC − AC | $67,360 | Cost to finish |
| VAC | BAC − EAC | -$12,360 | Expected budget overrun |

Quick Interpretation

| Metric | Good | Bad |
| --- | --- | --- |
| SV | Positive | Negative |
| SPI | > 1 | < 1 |
| CV | Positive | Negative |
| CPI | > 1 | < 1 |
| VAC | Positive | Negative |

Positive variance is good. Negative variance is bad.
Index greater than 1 is good. Index less than 1 is bad.