Project Risk Management

What is Risk?

Risk is an uncertain event or condition that, if it occurs, has a positive or negative effect on one or more project objectives.

Project objectives include:

- Scope

- Schedule

- Cost

- Quality

- Resources

- Customer Satisfaction

- Business Value

Formula

Risk = Probability × Impact

Example:

There is a 40% chance that the cloud provider may go down.

Impact = Delay of 5 days.

This is a project risk.

Risk is NOT Always Bad

Many people think risk only means problems.

Risk can be

- Negative (Threat)

- Positive (Opportunity)

Negative Risk (Threat)

May cause loss.

Examples

- Key developer resigns

- Server crashes

- Budget cuts

- Security breach

- Requirement changes

Result

- Delay

- Increased cost

- Poor quality

Positive Risk (Opportunity)

May create additional benefits.

Examples

- New AI tool increases productivity

- Customer increases project budget

- Vendor offers free cloud credits

- Developer finishes work early

- Better technology reduces infrastructure cost

Result

- Lower cost

- Faster delivery

- Better quality

- Higher customer satisfaction

Examples

Threat

Microsoft Azure service becomes unavailable.

Result

Deployment delayed.

Opportunity

GitHub Copilot generates code 40% faster.

Result

Sprint completed before deadline.

"It is Better to Hunt Risks First Before They Hunt You"

Successful project managers do not wait for problems.

They identify risks before the project starts.

Instead of reacting,

they prepare.

Imagine

Two project managers.

Manager A

Ignores risks.

When database crashes

Everyone panics.

Project delayed.

Customer unhappy.

Manager B

Already identified

Database failure risk.

Prepared

- Daily backup

- Disaster recovery

- Cloud failover

When database crashes,

Recovery takes only 10 minutes.

No project delay.

This is proactive risk management.

Example

Without risk planning

Requirement changes

↓

No buffer

↓

Deadline missed

↓

Penalty

With risk planning

Requirement changes

↓

Change management process

↓

Extra contingency reserve

↓

Project succeeds

Risk Concepts

1. Threat

Negative uncertainty.

Example

Production server hacked.

2. Opportunity

Positive uncertainty.

Example

Vendor offers 30% discount.

3. Risk Appetite

How much risk an organization is willing to take.

Example

Startup

High appetite.

Will experiment with AI.

Bank

Low appetite.

Will avoid risky technology.

4. Risk Tolerance

Variation the organization can accept.

Example

Project budget

$100,000

Tolerance

±5%

Means

Can accept

$95,000–105,000

5. Risk Threshold

Point beyond which action must be taken.

Example

If project delay exceeds

10 days

Escalate to steering committee.

6. Residual Risk

Risk remaining after response.

Example

Installed firewall.

Still

5% hacking possibility exists.

Remaining risk

Residual Risk.

7. Secondary Risk

New risk created because of response.

Example

Response

Move application to cloud.

New risk

Cloud vendor lock-in.

That is secondary risk.

8. Known Risk

Already identified.

Example

Monsoon may delay hardware delivery.

9. Unknown Risk

Cannot be predicted.

Example

Pandemic

War

Earthquake

Need Management Reserve.

10. Risk Averse

Avoids taking risks.

Example

Government projects.

Banks.

Healthcare.

Why Positive Risk is Important

Many organizations ignore opportunities.

But opportunities can

- Save money

- Increase profit

- Improve quality

- Finish earlier

- Increase customer satisfaction

Examples

AI code generation

↓

Less coding effort

↓

Higher productivity

Cloud credits

↓

Reduced infrastructure cost

↓

Higher project profit

Automation testing

↓

Less manual testing

↓

Better quality

Types of Risks in IT Projects

| Risk Type | Example |
| --- | --- |
| Technical Risk | Wrong architecture |
| Schedule Risk | Delayed development |
| Cost Risk | Budget overrun |
| Resource Risk | Developer resigns |
| Quality Risk | Too many defects |
| Security Risk | Data breach |
| Operational Risk | Server outage |
| Vendor Risk | Vendor misses delivery |
| Compliance Risk | HIPAA violation |
| Legal Risk | Software license issue |
| Requirement Risk | Frequent changes |
| Performance Risk | Application becomes slow |
| Infrastructure Risk | Cloud outage |
| Communication Risk | Customer unavailable |
| Business Risk | Customer cancels project |

Detailed Example

Technical Risk

Architecture cannot handle 10 million users.

Impact

System redesign.

Security Risk

SQL Injection attack.

Impact

Customer data leaked.

Operational Risk

Production server down.

Impact

Business stops.

Resource Risk

Senior architect resigns.

Impact

Knowledge lost.

Why Risk Identification is Necessary

Without identifying risks,

You cannot

- Prepare

- Estimate

- Respond

- Reduce uncertainty

Benefits

- Better planning

- Better estimation

- Less project failure

- Better decision making

- Better customer confidence

Project Risk Management Process

There are 7 major processes.

1 Plan Risk Management

↓

2 Identify Risks

↓

3 Perform Qualitative Risk Analysis

↓

4 Perform Quantitative Risk Analysis

↓

5 Plan Risk Responses

↓

6 Implement Risk Responses

↓

7 Monitor Risks

1 Plan Risk Management

Plan Risk Management is the process of defining how to conduct risk management activities for a project.

Simple Example

Imagine you are organizing a college sports tournament.

Before the tournament starts, you decide:

- Who will handle emergencies?

- Who will report problems?

- What if it rains?

- How often will meetings be held?

- How will risks be recorded?

You haven't identified every problem yet—you are simply creating a plan for managing risks.

The same idea applies to projects.

Why is Plan Risk Management Important?

Without planning:

- Team members may identify risks differently.

- No one knows who owns each risk.

- Risks may not be reviewed regularly.

- High-priority risks might be ignored.

- Different teams may use different methods.

With a Risk Management Plan:

- Everyone follows the same process.

- Risks are identified consistently.

- Responsibilities are clear.

- Decision-making becomes faster.

Outputs

- Risk Management Plan

Contents of a Risk Management Plan

1. Risk Management Methodology

Defines how risks will be managed.

Example:

- Brainstorming

- SWOT Analysis

- Risk Register

- Probability-Impact Matrix

2. Roles and Responsibilities

Who will do what?

Example:

| Role | Responsibility |
| --- | --- |
| Project Manager | Overall risk management |
| Technical Lead | Technical risks |
| Security Lead | Security risks |
| QA Lead | Quality risks |
| DevOps Engineer | Infrastructure risks |

3. Budget

How much money is reserved for risk management?

Example:

Total Project Budget

$500,000

Risk Management Budget

$20,000

Used for

- Security testing

- Backup servers

- Risk workshops

- Penetration testing

4. Schedule

When will risks be reviewed?

Example

- Weekly Scrum meeting

- Monthly Risk Review Meeting

- End of every Sprint

- Before each Release

5. Risk Categories

Group similar risks.

Example

Technical

Security

Operational

Schedule

Cost

Resource

Vendor

Compliance

Business

This grouping forms a Risk Breakdown Structure (RBS).

6. Probability Scale

Defines the likelihood of occurrence.

Example

| Probability | Meaning |
| --- | --- |
| Very Low | 10% |
| Low | 30% |
| Medium | 50% |
| High | 70% |
| Very High | 90% |

7. Impact Scale

Defines the severity if the risk occurs.

Example

| Impact | Cost/Schedule Effect |
| --- | --- |
| Very Low | Less than 1-day delay |
| Low | 1–3 days |
| Medium | Up to 1 week |
| High | 2–3 weeks |
| Very High | More than 1 month |

8. Risk Matrix

Combines probability and impact.

| Probability | Low Impact | Medium Impact | High Impact |
| --- | --- | --- | --- |
| High | Medium | High | Very High |
| Medium | Low | Medium | High |
| Low | Low | Low | Medium |

This helps prioritize risks.

9. Reporting Format

Defines how risks will be documented.

Example:

Each risk should include:

- Risk ID

- Description

- Cause

- Probability

- Impact

- Priority

- Response Strategy

- Risk Owner

- Current Status

10. Risk Review Frequency

Example

- Every Sprint Planning

- Weekly Project Meeting

- Monthly Steering Committee Meeting

- Before Production Release

Software Development Example

Project

Develop an Online Banking System.

Budget

$1,000,000

Duration

12 months

Team

40 people

2 Identify Risks

Goal

Find every possible risk.

Tools

- Brainstorming

- Expert judgment

- SWOT

- Checklists

- Lessons learned

- Interviews

- Assumption analysis

Output

Risk Register

Example

| Risk | Cause |
| --- | --- |
| Server failure | Old hardware |
| Scope change | Poor requirements |
| Developer resigns | Better offer |

3 Perform Qualitative Risk Analysis

Its purpose is to evaluate and prioritize identified risks based on their probability of occurring and their impact on project objectives. Unlike quantitative analysis, it does not use mathematical calculations or dollar values. Instead, it uses relative ratings such as High, Medium, and Low.

Uses

High

Medium

Low

Tools

- Probability Impact Matrix

- Risk Categorization

- Expert Judgment

- Urgency Assessment

Imagine you identified 50 risks in your software project.

Can you work on all 50 immediately?

No.

You must determine:

- Which risks are the most dangerous?

- Which risks need immediate action?

- Which risks can wait?

- Which risks can simply be monitored?

That is the purpose of Qualitative Risk Analysis.

Example

| Risk | Probability | Impact | Priority |
| --- | --- | --- | --- |
| Hacker attack | High | High | Very High |
| Rain | Low | Medium | Low |

Types of Qualitative Risk Analysis

Probability Assessment

Chance of occurrence.

Example

40%

Impact Assessment

Effect if occurs.

Example

Delay

High

Probability Impact Matrix

| Probability | Impact | Score |
| --- | --- | --- |
| High | High | Extreme |
| High | Medium | High |
| Low | Low | Low |

Risk Urgency Assessment

Which risk needs immediate attention?

Example

Cyber attack

Immediate.

Risk Categorization

Group risks.

Example

Technical

Security

Operational

Vendor

Expert Judgment

Senior architects evaluate risk.

Steps of Qualitative Risk Analysis

Step 1

Review the Risk Register.

Example:

- Security attack

- Vendor delay

- Requirement change

Step 2

Estimate probability.

Example:

Requirement changes

Probability = High.

Step 3

Estimate impact.

Example:

Requirement changes

Impact = High.

Step 4

Use the Probability-Impact Matrix.

Result:

Priority = Very High.

Step 5

Assign a priority.

Example:

| Priority | Action |
| --- | --- |
| Very High | Immediate response |
| High | Response plan required |
| Medium | Monitor and plan |
| Low | Observe only |

Step 6

Update the Risk Register.

Include:

- Probability

- Impact

- Priority

- Risk owner

- Planned response

Complete IT Software Example

Project: Online Banking System

Identified risks:

| Risk | Probability | Impact | Priority | Owner |
| --- | --- | --- | --- | --- |
| Cyber attack | High | Very High | Very High | Security Lead |
| Requirement changes | High | High | Very High | Product Owner |
| Cloud outage | Low | Very High | High | DevOps Engineer |
| Developer resignation | Medium | High | High | Engineering Manager |
| Minor UI issue | High | Low | Medium | QA Lead |
| Office internet outage | Low | Low | Low | IT Support |

The team first addresses:

- Cyber attack

- Requirement changes

- Developer resignation

Lower-priority risks continue to be monitored.

Outputs

The main output is an updated Risk Register.

Example:

| Risk | Probability | Impact | Priority | Response |
| --- | --- | --- | --- | --- |
| Hacker attack | High | Very High | Very High | Mitigate |
| Vendor delay | Medium | High | High | Transfer |
| Minor UI bug | High | Low | Medium | Accept |
| Rain delay | Low | Low | Low | Monitor |

Advantages

- Easy to understand.

- Quick to perform.

- No advanced mathematics required.

- Works well for most projects.

- Helps teams focus on the most critical risks.

Limitations

- Subjective; different people may rate the same risk differently.

- Does not estimate exact cost or schedule impact.

- Less precise than quantitative analysis.

- Depends on expert judgment.

4 Perform Quantitative Risk Analysis

Perform Quantitative Risk Analysis is the process of numerically analyzing the combined effect of identified individual project risks and other sources of uncertainty on overall project objectives. Quantitative Risk Analysis measures project risks using numbers, percentages, probabilities, money, and statistical models.

Used in large projects.

Unlike qualitative analysis (High, Medium, Low), quantitative analysis answers questions like:

- How much money could we lose?

- How much schedule delay is expected?

- What is the probability of finishing on time?

- What is the expected project cost?

- How much contingency reserve should be kept?

Simple Example

Suppose your project has identified these risks.

| Risk | Probability | Impact |
| --- | --- | --- |
| Hacker attack | High | High |
| Database failure | Medium | High |
| Requirement changes | High | Medium |

Qualitative analysis only says:

- Hacker attack → Very High

- Database failure → High

But management asks:

"How much money could these risks cost us?"

Now we need Quantitative Risk Analysis.

Why Perform Quantitative Risk Analysis?

It helps answer questions such as:

- What is the probability of completing the project on time?

- What is the expected financial loss?

- Which risk has the greatest financial impact?

- How much contingency budget should be reserved?

- Which project option gives the highest expected value?

Outputs

- Probability of meeting schedule

- Expected project cost

- Expected completion date

Steps of Quantitative Risk Analysis

Select High-Priority Risks

↓

Collect Numerical Data

↓

Choose Quantitative Technique

↓

Perform Calculations

↓

Interpret Results

↓

Update Risk Register

Types

Expected Monetary Value (EMV)

Expected Monetary Value (EMV) is a quantitative risk analysis technique used to calculate the expected financial impact of a risk by considering:

- Probability of the risk occurring

- Financial impact if the risk occurs

Formula

EMV = Probability × Impact

Where:

- Probability = Chance that the risk will happen

- Impact = Financial loss or benefit if the risk happens

Understanding EMV

A risk may have:

- High impact but low probability

- Low impact but high probability

EMV helps compare risks using a common value: money.

Example 1: Negative Risk (Threat)

Scenario: Online Food Delivery Application

Risk:

Payment gateway failure during peak hours

Data:

Probability:

20%

Impact:

If it happens, the company loses:

$100,000

Calculation

Convert percentage into decimal:

20% = 0.20

EMV=0.20×100,000
EMV=20,000

Result

EMV = $20,000

Meaning:

Although the company may not lose $100,000 every time, statistically this risk represents an expected loss of $20,000.

Example 2: Security Risk

Scenario

Risk:

Customer data breach

Impact:

- Legal penalty

- Customer compensation

- Reputation damage

Estimated financial impact:

$500,000

Probability:

10%

Calculation:

EMV=0.10×500,000
EMV=50,000

Interpretation

Expected financial exposure:

$50,000

Decision:

The company may spend up to $50,000 on:

- Security testing

- Encryption

- Monitoring

- Penetration testing

to reduce this risk.

Example 3: Resource Risk

Scenario

Risk:

Senior developer resigns.

Impact:

- Hiring cost

- Training cost

- Project delay

Financial impact:

$40,000

Probability:

30%

Calculation:

EMV=0.30×40,000
EMV=12,000

Result

Expected loss:

$12,000

Response:

- Knowledge sharing

- Documentation

- Backup resource

Example 4: Positive Risk (Opportunity)

EMV can also calculate opportunities.

For opportunities:

EMV=Probability×Benefit

Scenario: AI Coding Assistant Adoption

Opportunity:

Using AI coding tools can reduce development effort.

Benefit:

$200,000 savings

Probability:

70%

Calculation:

EMV=0.70×200,000
EMV=140,000

Result

Expected benefit:

$140,000

Response:

Exploit the opportunity

Actions:

- Train developers

- Create AI usage guidelines

- Measure productivity improvement

Multiple Risk EMV Example (Risk Exposure)

Online Food Delivery Project

| Risk | Probability | Impact | EMV |
| --- | --- | --- | --- |
| Payment failure | 20% | $100,000 | $20,000 |
| Security breach | 10% | $500,000 | $50,000 |
| Server outage | 15% | $200,000 | $30,000 |
| Developer resignation | 30% | $40,000 | $12,000 |

Total Risk Exposure

20,000+50,000+30,000+12,000

= $112,000

Interpretation

The project has an expected risk exposure of:

$112,000

The project manager may reserve:

- Contingency budget

- Additional resources

- Risk response budget

EMV with Decision Making Example

A food delivery company has two options:

Option A: Build Own Delivery System

Success

Probability: 80%

Benefit: $300,000

Failure

Probability: 20%

Loss: $100,000

Expected Monetary Value:

0.8×300,000)+(0.2×-100,000
=240,000-20,000
=220,000

Option B: Use Third-Party Delivery Partner

Success

Probability: 90%

Benefit: $200,000

Failure

Probability: 10%

Loss: $50,000

EMV:

0.9×200,000)+(0.1×-50,000
=180,000-5,000
=175,000

Decision

| Option | EMV |
| --- | --- |
| Build Own System | $220,000 |
| Third Party | $175,000 |

Choose:

Build Own Delivery System

because it has higher expected monetary value.

Decision Tree Analysis

Decision Tree Analysis is a quantitative risk analysis technique used to evaluate different choices when there are multiple possible outcomes under uncertainty.

When a project manager has multiple options:

- Build internally or outsource?

- Buy a tool or develop one?

- Use one vendor or another vendor?

- Invest now or wait?

Each option may have:

- Success probability

- Failure probability

- Financial benefit

- Financial loss

Decision Tree Analysis calculates the expected value of each option and helps choose the best decision.

Decision Tree Components

A decision tree contains:

1. Decision Node (□)

Represents a choice.

Example:

□ Choose Payment Provider

2. Chance Node (○)

Represents uncertainty.

Example:

○ Payment Gateway Works?

3. Branches

Represent possible outcomes.

Example:

Success → Profit

Failure → Loss

Formula

For each possible decision:

EMV = Probability × Financial Outcome

Total Expected Value:

Expected Value = Sum of all possible EMVs
Example 1: Online Food Delivery Application

Situation

A food delivery company wants to improve delivery speed.

They have two options:

Option A:

Develop an internal AI route optimization system.

Option B:

Buy an external delivery optimization service.

The project manager needs to decide.

Option A: Build Internal AI System

Possible outcomes

Success

Probability:

70%

Benefit:

$300,000

EMV:

0.70×300,000

= $210,000

Failure

Probability:

30%

Loss:

$100,000

EMV:

0.30×(-100,000)

= -$30,000

Total EMV of Option A

210,000-30,000

= $180,000

Option B: Buy Third-Party AI Service

Possible outcomes

Success

Probability:

90%

Benefit:

$200,000

EMV:

0.90×200,000

= $180,000

Failure

Probability:

10%

Loss:

$50,000

EMV:

0.10×(-50,000)

= -$5,000

Total EMV of Option B

180,000-5,000

= $175,000

Decision Tree Representation

Choose Solution

□

/                     \

/                       \

Build AI System            Buy AI Service

□                          □

|                          |

○                          ○

/       \                  /       \

Success    Failure          Success   Failure

70%         30%              90%       10%

+$300K     -$100K            +$200K    -$50K

EMV = $180K                  EMV = $175K

Decision

| Option | Expected Monetary Value |
| --- | --- |
| Build Internal AI | $180,000 |
| Buy External Service | $175,000 |

The company chooses:

Build Internal AI System

because it has a slightly higher expected value.

Monte Carlo Simulation

Monte Carlo Simulation is a quantitative risk analysis technique that uses computer-based mathematical modeling to simulate thousands or millions of possible project outcomes based on uncertainty and probability.

Simple Explanation

In normal project planning, we usually create one estimate:

Example:

"The food delivery application will be completed in 10 months."

But in reality:

- Some tasks finish early.

- Some tasks take longer.

- Requirements may change.

- Developers may face issues.

- External systems may fail.

Monte Carlo Simulation does not give one fixed answer.

Instead, it asks:

"If we run the project thousands of times with different possible conditions, what are the chances of success?"

Real-Life Analogy

Imagine predicting travel time.

You say:

"It takes 30 minutes to reach the airport."

But actual travel depends on:

- Traffic

- Weather

- Accidents

- Road conditions

A Monte Carlo simulation runs thousands of possible trips:

| Travel Time | Probability |
| --- | --- |
| 25 minutes | 10% |
| 35 minutes | 50% |
| 45 minutes | 80% |
| 60 minutes | 95% |

Now you know:

Leave early if you need a 95% chance of reaching on time.

Project managers use the same approach.

Why Use Monte Carlo Simulation?

It helps answer:

- What is the probability of completing the project on time?

- What is the probability of staying within budget?

- How much schedule buffer is required?

- Which risks affect the project most?

How Monte Carlo Simulation Works

Step 1: Create Project Model

The project manager provides:

- Activities

- Duration estimates

- Cost estimates

- Dependencies

Example:

Online Food Delivery Application:

| Activity | Duration |
| --- | --- |
| Mobile UI Development | 60 days |
| Backend API Development | 90 days |
| Payment Integration | 30 days |
| Testing | 45 days |
| Deployment | 15 days |

Step 2: Define Uncertainty

Instead of one estimate, define three estimates:

- Optimistic

- Most likely

- Pessimistic

Example:

Payment Integration

| Estimate | Days |
| --- | --- |
| Optimistic | 20 |
| Most likely | 30 |
| Pessimistic | 60 |

Why?

Because:

- Payment API may work smoothly.

- Vendor approval may delay.

- Security testing may take longer.

Step 3: Run Thousands of Simulations

The computer randomly selects values.

Example:

Simulation 1:

Payment integration = 25 days

Simulation 2:

Payment integration = 50 days

Simulation 3:

Payment integration = 35 days

This continues thousands of times.

Step 4: Analyze Results

The system produces probability results.

Example:

Online Food Delivery Application

Project duration:

Planned:

10 months

After 10,000 simulations:

| Completion Time | Probability |
| --- | --- |
| 10 months | 40% |
| 11 months | 75% |
| 12 months | 90% |
| 13 months | 98% |

Interpretation

If management promises:

Delivery in 10 months

Probability of success:

40%

Risk is high.

Delivery in 12 months

Probability of success:

90%

More realistic.

Decision

The project manager recommends:

"Increase the deadline from 10 months to 12 months to achieve a 90% confidence level."

Example: Budget Risk Analysis

Project

Food Delivery Application

Budget:

$1,000,000

Possible uncertainties:

- Cloud cost increase

- Additional developers

- Security testing

- Requirement changes

Cost Estimates

| Item | Low | Most Likely | High |
| --- | --- | --- | --- |
| Development | $600K | $700K | $850K |
| Infrastructure | $80K | $120K | $200K |
| Testing | $100K | $150K | $250K |

Monte Carlo Simulation runs:

10,000 budget scenarios.

Results:

| Total Cost | Probability |
| --- | --- |
| $1 Million | 50% |
| $1.2 Million | 80% |
| $1.5 Million | 95% |

Decision

The project manager should not reserve only:

$1 Million

because there is only a 50% chance of success.

Recommended budget:

$1.2 Million or higher.

Sensitivity Analysis

Sensitivity Analysis is a quantitative risk analysis technique used to determine which risks have the greatest impact on project objectives such as cost, schedule, or performance.

Which risk will affect the project the most if it happens?

How It Works

- Identify important project risks.

- Change one risk variable at a time.

- Measure how much the project outcome changes.

- Rank risks based on their impact.

The result is often shown using a Tornado Diagram.

Example: Online Food Delivery Application

Project Goal

Launch food delivery app in 10 months.

The team identifies possible causes of delay:

| Risk | Possible Delay |
| --- | --- |
| Requirement changes | 40 days |
| Payment gateway issues | 25 days |
| Developer resignation | 15 days |
| Server performance issues | 10 days |

Sensitivity Analysis Result

| Risk | Impact on Schedule | Priority |
| --- | --- | --- |
| Requirement changes | 40 days | Highest |
| Payment gateway issues | 25 days | High |
| Developer resignation | 15 days | Medium |
| Server issues | 10 days | Low |

Tornado Diagram Representation

Requirement Changes       ████████████████████ 40 days

Payment Gateway Issues    ████████████ 25 days

Developer Resignation     ███████ 15 days

Server Performance        █████ 10 days

Interpretation

The analysis shows:

Requirement changes have the highest impact.

Therefore, the project manager should focus on:

- Better requirement gathering

- Regular customer demos

- Change control process

- Product owner involvement

Another Cost Example

Project Budget:

$1 Million

Risks:

| Risk | Cost Impact |
| --- | --- |
| Security breach | $500,000 |
| Cloud cost increase | $150,000 |
| Tool license issue | $50,000 |

Sensitivity Analysis shows:

Security breach has the biggest impact.

Response:

Invest more in:

- Security testing

- Encryption

- Monitoring

Three Point Estimate (PERT)

Three-Point Estimate is a quantitative estimation technique used to calculate a more realistic project activity duration or cost by considering uncertainty and risk.

Instead of using one estimate, it uses three estimates:

- Optimistic Estimate (O)

  - Best-case scenario

  - Everything goes smoothly

- Most Likely Estimate (M)

  - Normal expected scenario

  - Based on experience and historical data

- Pessimistic Estimate (P)

  - Worst-case scenario

  - Problems and risks occur

Why Use Three-Point Estimate?

A single estimate can be unrealistic.

Example:

A developer says:

"Payment integration will take 20 days."

But in reality:

- API works perfectly → 15 days

- Normal development → 20 days

- API problems occur → 35 days

PERT considers all possibilities.

Example 1: Online Food Delivery Application

Task:

Develop Online Payment Integration.

The team estimates:

| Estimate | Days | Explanation |
| --- | --- | --- |
| Optimistic (O) | 15 days | Payment API works smoothly |
| Most Likely (M) | 25 days | Normal development and testing |
| Pessimistic (P) | 45 days | API issues, security fixes, delays |

Apply PERT Formula

E=O+4M+P6

Substitute values:

E=15+4(25)+456
E=15+100+456
E=1606
E=26.67

Result

Expected duration:

≈ 27 days

Interpretation

Although the most likely estimate was 25 days, after considering uncertainty:

The realistic planning estimate becomes:

27 days

The project manager can add appropriate schedule buffer.

Example 2: Mobile App Development

Task:

Develop Customer Order Tracking Feature.

Estimates:

| Scenario | Duration |
| --- | --- |
| Optimistic | 10 days |
| Most Likely | 20 days |
| Pessimistic | 40 days |

Calculation:

E=10+4(20)+406
E=10+80+406
E=1306
E=21.67

Expected Duration

≈ 22 days

Example 3: Cost Estimation

PERT can also estimate cost.

Task:

Security Testing

| Estimate | Cost |
| --- | --- |
| Optimistic | $20,000 |
| Most Likely | $35,000 |
| Pessimistic | $70,000 |

Formula:

E=20,000+4(35,000)+70,0006
E=20,000+140,000+70,0006
E=230,0006
E=38,333

Expected security testing cost:

$38,333

Difference

| Qualitative | Quantitative |
| --- | --- |
| Subjective | Numerical |
| High Medium Low | Percentages and Dollars |
| Faster | Time consuming |
| Simple | Mathematical |
| Used in most projects | Used in large projects |

Risk Response Planning

Goal

Decide what to do.

Negative Risk Strategies

1 Avoid

Remove the risk completely.

Example

Do not use unstable technology.

2 Mitigate

Reduce probability or impact.

Example

Automated backups.

3 Transfer

Shift responsibility.

Example

Cyber insurance.

Outsource hosting.

4 Accept

Do nothing.

Prepare contingency.

Example

Minor UI defects.

Positive Risk Strategies

1 Exploit

Ensure opportunity happens.

Example

Assign best developers to AI automation.

2 Enhance

Increase probability.

Example

Provide AI training.

3 Share

Partner with another company.

Example

Joint AI development.

4 Accept

Take benefit if opportunity occurs.

Example

Accept vendor discount.

Risk Response Process

Identify

↓

Analyze

↓

Prioritize

↓

Select Strategy

↓

Assign Owner

↓

Implement

↓

Monitor

Risk Monitoring

Purpose

Track

- Existing risks

- New risks

- Closed risks

- Response effectiveness

Activities

- Risk audits

- Risk reassessment

- Risk reviews

- Reserve analysis

- Lessons learned

- Update Risk Register

Risk Register Example

| ID | Risk | Probability | Impact | Priority | Response | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| R1 | Developer resigns | High | High | High | Cross-training & backup resource | Engineering Manager |
| R2 | Security attack | Medium | Very High | High | Firewall, MFA, Penetration Testing | Security Lead |
| R3 | Requirement changes | High | Medium | High | Formal Change Control Process | Product Owner |
| R4 | Cloud outage | Low | High | Medium | Multi-region deployment & DR Plan | DevOps Engineer |

Software Development Case Study

Project

Develop a Hospital Management System.

Duration

8 months

Budget

$500,000

Team

25 members

Step 1: Plan Risk Management

Create:

- Risk Management Plan

- Risk Matrix

- Risk Categories

- Reporting process

Step 2: Identify Risks

- Developers may resign.

- Customer may change requirements.

- Third-party API may fail.

- Database performance issues.

- Security vulnerabilities.

- AI-generated code quality concerns.

Step 3: Qualitative Analysis

| Risk | Probability | Impact | Priority |
| --- | --- | --- | --- |
| Requirement change | High | High | Very High |
| Developer resignation | Medium | High | High |
| API downtime | Medium | Medium | Medium |
| Power outage | Low | Medium | Low |

Focus first on the Very High and High priority risks.

Step 4: Quantitative Analysis

- Estimated loss from API outage: 25% probability × $80,000 impact = EMV = $20,000.

- Monte Carlo simulation predicts:

  - 70% chance of finishing in 8 months.

  - 90% chance of finishing in 8.5 months.

- PERT estimate for a critical feature:

  - Optimistic = 15 days

  - Most likely = 20 days

  - Pessimistic = 35 days

  - Expected duration = (15 + 4×20 + 35) / 6 = 21.7 days.

Step 5: Plan Risk Responses

| Risk | Strategy | Action |
| --- | --- | --- |
| Requirement changes | Mitigate | Frequent customer demos and change control board |
| Developer resignation | Mitigate | Documentation, knowledge sharing, cross-training |
| Cloud outage | Transfer/Mitigate | SLA with cloud provider and disaster recovery setup |
| AI productivity opportunity | Exploit | Adopt approved AI coding tools and developer training |

Step 6: Implement Risk Responses

- Weekly knowledge-sharing sessions.

- Automated backups.

- Security testing integrated into CI/CD.

- Sprint reviews every two weeks with stakeholders.

- AI coding guidelines and code review policies implemented.

Step 7: Monitor Risks

- Review the Risk Register in every sprint.

- Track new risks and close resolved risks.

- Measure response effectiveness.

- Escalate risks that exceed defined thresholds.

- Capture lessons learned for future projects.

Complete Risk Management Case Study: Online Food Delivery Application

Project Overview

Project Name

FoodExpress – Online Food Delivery Platform

Objective

Develop a mobile and web application that connects:

- Customers

- Restaurants

- Delivery partners

- Payment providers

The application allows customers to:

- Search restaurants

- Browse menus

- Place orders

- Make payments

- Track delivery

- Provide ratings and reviews

Project Details

| Item | Description |
| --- | --- |
| Project Duration | 10 Months |
| Budget | $1 Million |
| Team Size | 25 Members |
| Methodology | Agile Scrum |
| Platforms | Android, iOS, Web |
| Backend | .NET / Java Microservices |
| Database | SQL Server / PostgreSQL |
| Cloud | AWS / Azure |

Business Goals

The company wants to:

- Launch the app before competitors

- Handle 100,000 daily users

- Process online payments securely

- Provide delivery within 30 minutes

- Maintain high customer satisfaction

Why Risk Management is Required?

An online food delivery system has many uncertainties:

- Restaurant availability

- Delivery delays

- Payment failures

- High traffic during peak hours

- Security threats

- Customer complaints

- Third-party dependency

A small failure can impact thousands of customers.

Example:

Friday evening:

100,000 customers order food.

If the application crashes:

- Customers cannot order.

- Restaurants lose revenue.

- Delivery partners lose income.

- Company reputation is damaged.

Therefore, risks must be managed proactively.

Step 1: Plan Risk Management

Objective

Define how risks will be managed throughout the project.

Risk Management Approach

The team decides to use:

Risk Identification Techniques

- Brainstorming

- SWOT Analysis

- Expert interviews

- Historical data from similar apps

- Customer feedback analysis

Risk Review Frequency

| Activity | Frequency |
| --- | --- |
| Team risk discussion | Every sprint |
| Risk register update | Weekly |
| Management review | Monthly |
| Production risk review | Before release |

Roles and Responsibilities

| Role | Responsibility |
| --- | --- |
| Project Manager | Overall risk management |
| Product Owner | Business and customer risks |
| Solution Architect | Technical risks |
| Security Engineer | Payment/security risks |
| DevOps Engineer | Infrastructure risks |
| QA Lead | Quality risks |

Risk Categories

Risk Breakdown Structure:

Food Delivery Application Risks

||-- Technical Risks

||-- Security Risks

||-- Operational Risks

||-- Payment Risks

||-- Vendor Risks

||-- Resource Risks

||-- Customer Risks

||-- Compliance Risks

Step 2: Identify Risks

The team conducts a brainstorming session.

SWOT Analysis

Strengths

Internal advantages.

| Strength | Benefit |
| --- | --- |
| Experienced mobile developers | Faster app development |
| Cloud infrastructure | Scalability |
| Automated testing | Better quality |
| Existing payment integration experience | Faster delivery |

Weaknesses

Internal limitations.

| Weakness | Risk |
| --- | --- |
| New delivery algorithm | Incorrect delivery estimation |
| Small DevOps team | Production support challenges |
| Limited load testing experience | Performance issues |
| Dependency on third-party APIs | External failures |

Opportunities

Positive risks.

| Opportunity | Benefit |
| --- | --- |
| AI-based recommendation engine | Better food suggestions |
| Route optimization AI | Faster delivery |
| Chatbot support | Reduced customer support cost |
| Loyalty program | More customers |

Threats

Negative risks.

| Threat | Impact |
| --- | --- |
| Payment gateway failure | Customers cannot pay |
| Cyber attack | Customer data leakage |
| Competitor launches similar app | Market loss |
| Delivery partner shortage | Late deliveries |

Risk Register

| ID | Risk | Category |
| --- | --- | --- |
| R1 | Application crashes during peak hours | Technical |
| R2 | Payment transaction failure | Payment |
| R3 | Customer data breach | Security |
| R4 | Delivery delay | Operational |
| R5 | Restaurant API failure | Vendor |
| R6 | Developer resignation | Resource |
| R7 | Requirement changes | Scope |
| R8 | AI recommendation opportunity | Opportunity |

Step 3: Perform Qualitative Risk Analysis

The team evaluates:

- Probability

- Impact

- Priority

Risk Matrix

| Risk | Probability | Impact | Priority |
| --- | --- | --- | --- |
| Application crash | High | Very High | Critical |
| Payment failure | Medium | Very High | High |
| Data breach | Medium | Very High | High |
| Delivery delay | High | High | Critical |
| Developer resignation | Medium | Medium | Medium |
| Minor UI issues | High | Low | Medium |
| AI recommendations | High | High | Opportunity |

Example Analysis

Risk: Application Crash During Dinner Peak

Probability:

High

Impact:

Very High

Priority:

Critical

Reason:

Thousands of customers cannot order food.

Risk: Developer Leaving

Probability:

Medium

Impact:

Medium

Priority:

Medium

Reason:

Can be managed with knowledge transfer.

Step 4: Perform Quantitative Risk Analysis

Now we calculate numerical impact.

Risk 1: Payment Gateway Failure (EMV)

Risk:

Payment provider outage.

Probability:

15%

Impact:

Loss of sales = $200,000

Formula:

EMV = Probability × Impact

Calculation:

0.15 × 200,000

= $30,000

Meaning:

Expected financial exposure is $30,000.

Response:

Implement backup payment gateway.

Risk 2: Application Performance Risk (Monte Carlo Simulation)

Problem:

During weekends, traffic increases 5 times.

Simulation:

10,000 scenarios.

Results:

| Users | Probability |
| --- | --- |
| 50,000 users | 95% success |
| 100,000 users | 75% success |
| 150,000 users | 40% success |

Decision:

Increase infrastructure capacity.

Risk 3: Delivery Delay (Sensitivity Analysis)

Factors causing delay:

| Factor | Contribution |
| --- | --- |
| Traffic congestion | 40% |
| Poor restaurant preparation time | 30% |
| Delivery partner shortage | 20% |
| Other | 10% |

Conclusion:

Traffic and restaurant preparation are major contributors.

Step 5: Plan Risk Responses

Negative Risk Strategies

Risk 1: Application Crash

Strategy: Mitigate

Actions:

- Load testing using JMeter

- Auto-scaling servers

- Database optimization

- Performance monitoring

Owner:

DevOps Lead

Risk 2: Payment Failure

Strategy: Mitigate + Transfer

Actions:

- Integrate multiple payment providers

- Payment retry mechanism

- Transaction monitoring

- Vendor SLA agreement

Owner:

Payment Integration Team

Risk 3: Customer Data Breach

Strategy: Mitigate

Actions:

- Encrypt customer information

- Secure API gateway

- Regular penetration testing

- Security scanning

- Access control

Owner:

Security Team

Risk 4: Delivery Delay

Strategy: Mitigate

Actions:

- GPS tracking

- AI route optimization

- Delivery time prediction

- Partner performance monitoring

Owner:

Operations Team

Positive Risk Response

Opportunity:

AI recommendation engine improves sales.

Probability:

80%

Impact:

Increase order value by 20%

Strategy:

Exploit

Actions:

- Implement machine learning recommendation

- Analyze customer preferences

- Personalized food suggestions

Expected Benefit:

Higher revenue.

Step 6: Implement Risk Responses

The team executes actions.

Technical Improvements

Implemented:

- Load testing before release

- Cloud auto-scaling

- Database indexing

- Application monitoring

Result:

Application handles peak traffic.

Payment Improvements

Implemented:

- Multiple payment gateways

- Payment failure recovery

- Transaction alerts

Result:

Payment success rate improved.

Security Improvements

Implemented:

- Encryption

- Security testing

- Vulnerability scanning

Result:

Customer data protected.

Delivery Improvements

Implemented:

- Real-time GPS tracking

- Route optimization

- Delivery partner dashboard

Result:

Average delivery time reduced.

Step 7: Monitor Risks

Risk review happens every sprint.

Risk Monitoring Dashboard

| Risk | Initial Status | Current Status |
| --- | --- | --- |
| App crash | Critical | Controlled |
| Payment failure | High | Low |
| Data breach | High | Medium |
| Delivery delay | Critical | Medium |
| Developer dependency | Medium | Closed |

Production Scenario Example

Situation

Friday evening at 7 PM:

Traffic increases 300%.

Without Risk Management

High traffic

↓

Server overload

↓

Application crash

↓

Lost orders

↓

Customer complaints

With Risk Management

High traffic

↓

Auto scaling activates

↓

Additional servers added

↓

Application remains available

↓

Orders continue

Final Project Outcome

| Area | Result |
| --- | --- |
| Application Availability | 99.9% |
| Payment Success Rate | 98% |
| Delivery Time | Reduced by 20% |
| Security Issues | No major breach |
| Customer Satisfaction | Improved |
| Budget | Within planned budget |

Complete PMBOK Risk Management Flow

1. Plan Risk Management

↓

2. Identify Risks

↓

3. Qualitative Risk Analysis

↓

4. Quantitative Risk Analysis

↓

5. Plan Risk Responses

↓

6. Implement Risk Responses

↓

7. Monitor Risks