Project

A project is a temporary endeavor undertaken to create a unique product, service, or result.

Key characteristics

- Temporary – It has a definite beginning and end.

- Unique – It creates something different or a specific outcome.

- Goal-oriented – It is undertaken to achieve defined objectives.

- Progressive – The project becomes clearer and more detailed as it progresses.

- Uses resources – People, money, technology, materials, and time are required.

Example

Developing a new banking mobile application is a project because:

- It starts on a specific date.

- It has a planned completion date.

- A specific team works on it.

- It produces a unique application.

- Once the application is delivered, the project ends.

Project ≠ Operations:
Developing a banking application is a project.
Continuously operating and maintaining the banking application is an operation.

IT Project vs Traditional Project

| Area | IT Project | Traditional Project |
| --- | --- | --- |
| Main focus | Software, systems, data, technology | Construction, manufacturing, infrastructure |
| Output | Software/system/digital product | Physical product/structure |
| Requirements | Can change frequently | Usually more stable |
| Technology | Major dependency | May have less technology dependency |
| Customer feedback | Frequent | Often less frequent |
| Change | High | Comparatively low |
| Testing | Continuous and extensive | Physical inspection/testing |
| Example | Mobile banking application | Building a hospital |

Example

IT Project:
Develop an online shopping website.

Requirements may change:

"Add online payment." → "Add mobile wallet." → "Add AI chatbot."

Traditional Project:
Build a bridge.

Changing the bridge design after construction has started can be expensive and difficult.

Important point

IT projects generally operate in an environment of high uncertainty and rapid change, so approaches such as Agile can be particularly useful.

Example of an IT Project

Project: Online Banking Application

Objective:
Develop a secure mobile banking application within 9 months.

Major deliverables

- User registration

- Login and authentication

- Account balance

- Fund transfer

- Bill payment

- Transaction history

- Notifications

- Security testing

- Production deployment

Project team

- Project Manager

- Business Analyst

- Developers

- UI/UX Designer

- QA/Testers

- DevOps Engineer

- Security Engineer

- Product Owner

Constraints

- Time: 9 months

- Budget: $500,000

- Scope: Defined banking functionality

- Quality: Security and performance requirements

Project Management

Project management is the application of knowledge, skills, tools, and techniques to project activities to meet project requirements.

In simple words:

Project management means planning, organizing, executing, monitoring, controlling, and closing a project successfully.

The Project Manager coordinates people, budget, schedule, risks, communication, stakeholders, and deliverables throughout the project.

Importance of IT Project Management

IT project management is important because IT projects often involve:

- Complex technology

- Changing requirements

- Multiple stakeholders

- Tight deadlines

- Limited budgets

- Security risks

- Integration challenges

- Quality expectations

Without proper project management

A project may suffer from:

Scope creep → Delays → Cost overruns → Quality problems → Customer dissatisfaction → Project failure

Example

Suppose a company wants to develop an e-commerce application.

Without proper project management:

- Developers don't clearly understand requirements.

- Features keep getting added.

- Testing starts too late.

- Budget increases.

- Release date is missed.

- Customers are unhappy.

With effective project management:

Clear scope → Proper planning → Controlled changes → Risk management → Continuous monitoring → Successful delivery

Project Manager

A Project Manager (PM) is the person responsible for leading and coordinating the project team and managing the project to achieve its objectives.

A PM does not necessarily do all the technical work.

Instead, the PM ensures:

The right people do the right work at the right time within the agreed constraints.

Role of a Project Manager in IT

An IT Project Manager typically performs the following activities:

1. Project Planning

Creates the project plan, schedule, milestones, and approach.

2. Scope Management

Defines what is included and excluded from the project.

3. Schedule Management

Ensures activities are completed on time.

4. Cost Management

Monitors and controls the project budget.

5. Team Management

Builds, coordinates, motivates, and supports the project team.

6. Risk Management

Identifies risks and prepares mitigation strategies.

7. Stakeholder Management

Manages expectations of customers, sponsors, management, users, and other stakeholders.

8. Communication

Ensures the right information reaches the right people at the right time.

9. Quality Management

Ensures project deliverables meet defined quality requirements.

10. Change Management

Evaluates and controls changes to scope, schedule, cost, and requirements.

11. Issue Management

Identifies, tracks, and resolves project issues.

12. Project Closure

Ensures final delivery, documentation, lessons learned, and formal closure.

Skills of an IT Project Manager

An effective IT Project Manager needs a combination of technical, business, leadership, and interpersonal skills.

A. Technical Skills

- Software development lifecycle

- Agile/Scrum

- Testing

- DevOps

- Cloud concepts

- Database concepts

- Cybersecurity awareness

- IT architecture awareness

- Project management tools

The PM doesn't need to be the best developer, but should understand the technology sufficiently to manage the project effectively.

B. Management Skills

- Planning

- Estimation

- Scheduling

- Budget management

- Risk management

- Quality management

- Resource management

- Change management

C. Leadership Skills

- Team building

- Motivation

- Decision making

- Conflict resolution

- Delegation

- Coaching

- Problem solving

D. Communication Skills

- Presentation

- Negotiation

- Active listening

- Stakeholder communication

- Report writing

- Meeting facilitation

E. Business Skills

- Understanding business objectives

- ROI awareness

- Cost-benefit analysis

- Strategic thinking

- Customer orientation

Project Management Frameworks

Three commonly discussed approaches/frameworks are:

- PMBOK

- PRINCE2

- Agile

Note: PMBOK is primarily a body of knowledge/standard and guide, PRINCE2 is a project management method, and Agile is a set of values and principles/approaches rather than one single project-management methodology.

PMBOK

PMBOK = Project Management Body of Knowledge

Published by the Project Management Institute (PMI).

PMBOK provides principles, performance domains, practices, and guidance for managing projects.

Focus

- Value delivery

- Stakeholders

- Planning

- Team

- Project work

- Delivery

- Measurement

- Uncertainty

PMBOK can be applied to:

- IT

- Construction

- Healthcare

- Manufacturing

- Finance

- Government projects

PRINCE2

PRINCE2 = Projects IN Controlled Environments

It is a structured project management method.

Main characteristics

- Clearly defined roles

- Business justification

- Controlled stages

- Defined management products

- Focus on governance

- Controlled changes

- Lessons learned

Example

For a government software project:

Business Case → Project Initiation → Stage 1 → Stage 2 → Stage 3 → Final Delivery

PRINCE2 provides a strong governance and control structure.

Agile

Agile is an approach based on iterative and incremental delivery, continuous feedback, collaboration, and responding to change.

Typical Agile cycle

Plan → Develop → Test → Review → Feedback → Improve

Then repeat.

Example

Instead of waiting 12 months to deliver an entire banking system:

Sprint 1: Login
Sprint 2: Account balance
Sprint 3: Fund transfer
Sprint 4: Bill payment
Sprint 5: Notifications

Customers can provide feedback throughout development.

Popular Agile approaches

- Scrum

- Kanban

- Extreme Programming (XP)

- SAFe

PMBOK vs PRINCE2 vs Agile

| Aspect | PMBOK | PRINCE2 | Agile |
| --- | --- | --- | --- |
| Nature | Body of knowledge/guidance | Method | Approach |
| Focus | Principles and practices | Governance and control | Adaptability and delivery |
| Change | Managed | Controlled | Expected and embraced |
| Planning | Can be predictive, adaptive, or hybrid | Structured | Iterative |
| Delivery | Flexible | Stage-based | Incremental |
| Best suited | Broad range of projects | Structured environments | Dynamic/uncertain projects |
| Example | IT, construction, healthcare | Government/large structured projects | Software/product development |

Ten Knowledge Areas of PMBOK

1. Project Integration Management

Coordinates all parts of the project.

Example:
Ensuring development, testing, deployment, budget, schedule, and stakeholders work together.

2. Project Scope Management

Defines what the project will and will not deliver.

Example:
An e-commerce project includes online payment but excludes delivery management.

Main concern: Prevent uncontrolled scope creep.

3. Project Schedule Management

Plans and controls project activities and timelines.

Example:

| Activity | Duration |
| --- | --- |
| Requirements | 2 weeks |
| Design | 3 weeks |
| Development | 8 weeks |
| Testing | 4 weeks |
| Deployment | 1 week |

4. Project Cost Management

Plans, estimates, budgets, and controls project costs.

Example:

Developer cost = $200K
Infrastructure = $50K
Testing = $50K
Other costs = $50K

Total budget = $350K

5. Project Quality Management

Ensures the project meets required quality standards.

Example:

For a banking application:

- 90%+ test automation

- Zero critical security defects

- Performance requirement met

- Required test coverage achieved

6. Project Resource Management

Manages people and physical resources.

Example:

- 1 Project Manager

- 1 Business Analyst

- 5 Developers

- 3 QA Engineers

- 1 DevOps Engineer

The PM ensures appropriate resources are available when needed.

7. Project Communications Management

Ensures project information is properly generated, distributed, stored, and understood.

Example:

Weekly:

PM → Project status → Management

Daily:

Team → Daily Scrum

Monthly:

PM → Steering Committee

8. Project Risk Management

Identifies, analyzes, and responds to project risks.

Example

Risk: Key developer may leave.

Probability: Medium
Impact: High

Response:

- Cross-train another developer.

- Document critical knowledge.

- Maintain backup resources.

9. Project Procurement Management

Manages purchasing products, services, or resources from external suppliers.

Example:

A company needs a third-party cloud security service.

The project team may need to:

Identify requirement → Prepare procurement → Evaluate vendors → Select vendor → Manage contract

10. Project Stakeholder Management

Identifies stakeholders and manages their engagement.

Example stakeholders

- Customer

- Project sponsor

- End users

- Developers

- QA team

- Management

- Vendors

- Regulatory bodies

The PM needs to understand their interests, expectations, influence, and concerns.

Case Study – Successful IT Project

iPhone – Successful IT Product Case Study

Background

Apple introduced the first iPhone in 2007. It combined a mobile phone, iPod, and internet capabilities into one device.

Project Objective

Create a mobile device that would provide:

- Phone functionality

- Internet access

- Music

- Touch-based user interface

- Simple and attractive user experience

Major Challenges

- Creating a new touch interface

- Integrating hardware and software

- Developing a new mobile operating system

- Keeping the product simple

- Meeting a fixed launch deadline

- Maintaining high quality

Project Management Lessons

1. Clear vision
Apple had a clear product vision.

2. Scope control
The initial iPhone did not try to include every possible feature.

3. Cross-functional team
Hardware, software, design, and business teams worked together.

4. Customer experience
The project focused heavily on usability.

5. Innovation
The project challenged existing assumptions about mobile phones.

Lesson

A successful IT project starts with a clear problem, strong vision, focused scope, and customer value.

Nokia – Failed/Declining Product Strategy Case Study

Background

Nokia was once one of the world's leading mobile-phone companies.

However, Nokia struggled to respond effectively to the rapid transition from traditional mobile phones to smartphones.

What happened?

The market changed significantly:

Traditional phones → Smartphones → App ecosystems → Touch interfaces

Nokia had strong hardware capabilities but faced challenges around software, operating systems, ecosystem development, and strategic execution.

Major Problems

1. Slow response to market change

The smartphone market changed quickly.

2. Software challenges

Nokia's Symbian platform struggled to compete effectively with newer smartphone platforms.

3. Organizational challenges

Decision-making and internal coordination became difficult.

4. Ecosystem disadvantage

Modern smartphones were increasingly about:

Hardware + Operating System + Apps + Developer Ecosystem

5. Strategic decisions

Nokia later partnered with Microsoft and adopted Windows Phone, but the strategy did not restore its former smartphone position.

Project Management Lessons

- Continuously monitor external changes.

- Don't focus only on current success.

- Technology projects need strong strategic alignment.

- User expectations can change rapidly.

- Organizational communication matters.

- A technically good product can still fail commercially.

Lesson

Past success does not guarantee future success. IT projects must continuously adapt to technology and customer changes.

Internet Explorer vs Chrome – Browser Case Study

This is a very good example of competition, innovation, and failure to adapt.

Internet Explorer

Microsoft's Internet Explorer was once the dominant web browser.

For many years, it had a huge market share because it was bundled with Windows.

But competitors such as:

- Firefox

- Chrome

- Safari

introduced new features and competed aggressively.

Problems

Internet Explorer became associated with:

- Slow innovation

- Performance issues

- Security concerns

- Compatibility problems

- Slow release cycles

Microsoft eventually replaced Internet Explorer with Microsoft Edge.

Google Chrome – Successful Browser Case Study

Google launched Chrome in 2008.

Objective

Build a browser that was:

- Fast

- Simple

- Secure

- Stable

- Easy to use

- Suitable for modern web applications

Key Strategy

Chrome focused heavily on:

Performance + Simplicity + Security + Continuous Updates

Project Management Lessons

1. Customer needs

Users wanted faster and simpler browsing.

2. Continuous delivery

Chrome adopted frequent updates rather than waiting years for major releases.

3. Innovation

Chrome introduced strong process isolation and performance improvements.

4. Quality

Security and stability were major priorities.

Lesson

In IT, continuous improvement can be more important than simply delivering a product once.

What These Cases Teach a Project Manager

These examples are excellent for explaining why IT Project Management is different from traditional project management.

Traditional thinking

Plan → Build → Deliver → Finish

Modern IT thinking

Plan → Build → Test → Release → Get feedback → Improve → Repeat

Because technology and customer expectations change quickly, an IT Project Manager must manage not only:

Time + Cost + Scope + Quality

but also:

Innovation + Change + Customer Value + Risk + Adaptability

Successful vs Failed IT Project

| Factor | Successful Project | Failed Project |
| --- | --- | --- |
| Vision | Clear | Unclear/changes significantly |
| Requirements | Well managed | Complex/poorly aligned |
| Stakeholders | Strong engagement | Insufficient alignment |
| Change | Managed continuously | Difficult to control |
| Risk | Identified early | Risks may materialize |
| Communication | Effective | Poor coordination |
| Technology | Supports business | Technology may not meet needs |
| User adoption | High | Low/resistance |
| Governance | Strong | Weak/complex |
| Outcome | Business value delivered | Objectives not adequately achieved |

Portfolio → Program → Project

Portfolio

A portfolio is a collection of projects, programs, and other work that are grouped together to achieve strategic business objectives.

Portfolio = Are we investing in the right work?

Program

A program is a group of related projects managed together to obtain benefits that would be difficult to achieve by managing them separately.

Program = Are we coordinating related projects to achieve greater benefits?

Project

A project is a temporary endeavor undertaken to create a unique product, service, or result.

Project = Are we delivering the specific agreed outcome?

Here:

- Portfolio manages the strategic investment.

- Program manages related projects.

- Project delivers a specific outcome.

IT Example

Imagine a bank wants to become a Digital Bank.

Portfolio: Digital Transformation Portfolio

The bank's strategic goal is:

"Transform the bank into a fully digital banking organization."

The portfolio may contain:

Digital Transformation Portfolio

│

├── Digital Banking Program

│   ├── Mobile Banking Project

│   ├── Internet Banking Project

│   ├── Digital Payment Project

│   └── Digital Onboarding Project

│

├── Data & Analytics Program

│   ├── Data Warehouse Project

│   ├── Customer Analytics Project

│   └── AI Recommendation Project

│

└── Cybersecurity Project

Project Example

Project: Mobile Banking Application

The project has a specific objective:

Develop and launch a mobile banking application within 9 months.

Activities

Requirements

↓

Design

↓

Development

↓

Testing

↓

Security Testing

↓

Deployment

↓

Project Closure

Once the application is delivered and the project objectives are achieved, the project is closed.

Program Example

Suppose the bank wants to provide customers with a complete digital banking experience.

It creates a:

Digital Banking Program

The program contains several related projects:

DIGITAL BANKING PROGRAM

│

┌───────────────┼────────────────┐

│               │                │

▼               ▼                ▼

Mobile Banking   Internet Banking   Digital Payment

Project           Project           Project

│               │                │

└───────────────┼────────────────┘

▼

Common Digital Benefits

The projects are related because they all contribute to the same digital banking objective.

The Program Manager coordinates things such as:

- Shared resources

- Dependencies

- Common technology

- Risks

- Integration

- Benefits

- Stakeholders

Portfolio Example

At an even higher level, the bank may have many strategic initiatives:

BANK IT PORTFOLIO

│

┌─────────────────┼─────────────────┐

▼                 ▼                 ▼

Digital Banking     Data & AI       Cybersecurity

Program           Program           Program

│                 │                 │

Projects          Projects          Projects

The Portfolio Manager / senior leadership decides:

- Which initiatives should receive funding?

- Which projects should have higher priority?

- Which projects should be stopped?

- Where should resources be allocated?

- Which initiatives provide the greatest strategic value?

Portfolio vs Program vs Project

| Aspect | Portfolio | Program | Project |
| --- | --- | --- | --- |
| Main focus | Strategy | Benefits | Deliverable |
| Contains | Projects, programs, other work | Related projects | Activities/tasks |
| Objective | Strategic objectives | Common benefits | Specific outcome |
| Time | May be ongoing | May be long-term | Temporary |
| Change | Portfolio-level strategic changes | Coordinated changes | Controlled project changes |
| Success | Strategic value | Benefits realization | Scope, schedule, cost, quality & objectives |
| Example | Digital Transformation Portfolio | Digital Banking Program | Mobile Banking Project |

Goals and Objectives

Goal

In project management, a goal is a broad desired result or direction that the organization, project, or team wants to achieve.

A goal provides overall direction and purpose, but it may not be sufficiently detailed to measure project performance by itself.

IT Company Example

Goal: Improve the quality of software products.

This tells us what we want to achieve, but not exactly how much improvement is expected or by when.

Objective

A project objective is a specific result that the project intends to achieve. Good project objectives should be clear, measurable, realistic, and aligned with organizational and stakeholder needs.

Objectives help translate a broad goal into measurable project outcomes.

Example

Goal:
Improve software quality.

Project Objectives:

- Reduce production defect leakage.

- Increase automated test coverage.

- Improve compliance with code-review practices.

- Reduce the time required to resolve critical defects.

Goal vs Objective

| Goal | Objective |
| --- | --- |
| Broad desired outcome | Specific result |
| Provides direction | Defines what must be achieved |
| Usually less detailed | More precise and measurable |
| May contain several objectives | Supports achievement of a goal |
| Strategic in nature | Can be project-specific |

Simple example

Goal: Improve customer experience.

Objective: Reduce the average response time for customer support issues from 8 hours to 4 hours by December 2026.

SMART Objectives

SMART is a useful technique for developing clear and measurable objectives.

SMART means:

S – Specific
Clearly state what needs to be achieved.

M – Measurable
Define how achievement will be measured.

A – Achievable
The target should be realistically attainable with available resources and constraints.

R – Relevant
The objective should support the project and organizational/business needs.

T – Time-bound
Specify when the objective must be achieved.

SMART IT Project Objective

Non-SMART

Improve software quality.

The statement is too broad.

We don't know:

- How much improvement?

- Which quality measure?

- By when?

- How will success be measured?

SMART

Reduce production defect leakage by 25% by December 31, 2026, through increased test automation, improved code reviews, and defect-prevention activities.

SMART Analysis

| SMART | Application |
| --- | --- |
| Specific | Reduce production defect leakage |
| Measurable | 25% reduction |
| Achievable | Through defined improvement activities |
| Relevant | Supports software quality |
| Time-bound | December 31, 2026 |

Examples of SMART Objectives in IT Projects

Quality

Reduce critical production defects by 30% by the end of Q4 2026.

Testing

Increase automated regression test coverage from 50% to 75% by December 2026.

Schedule

Complete at least 95% of planned project milestones within the approved schedule by the end of 2026.

Performance

Reduce average API response time from 2 seconds to less than 1 second by September 30, 2026.

Security

Reduce critical security vulnerabilities identified after release by 50% by December 2026 through automated security testing and mandatory remediation.

Training

Train 90% of project team members on the approved AI-assisted development tools by October 31, 2026, with each participant completing one practical exercise.

Examples of Non-SMART Objectives

❌ Improve software quality.

Problem: No measurement or deadline.

❌ Increase automation.

Problem: No baseline or target.

❌ Reduce defects.

Problem: No percentage or timeframe.

❌ Deliver the project faster.

Problem: "Faster" is not measurable.

❌ Improve customer satisfaction.

Problem: No defined customer satisfaction measure or target.

❌ Train employees in AI.

Problem: No number of employees, completion criteria, or deadline.

Converting Non-SMART to SMART

| Non-SMART | SMART |
| --- | --- |
| Improve quality | Reduce production defect leakage by 25% by Dec 2026 |
| Increase automation | Increase regression automation from 50% to 75% by Dec 2026 |
| Reduce defects | Reduce critical production defects by 30% by Q4 2026 |
| Deliver faster | Improve schedule adherence to ≥95% by Dec 2026 |
| Improve customer satisfaction | Increase customer satisfaction from 82% to 90% by Dec 2026 |
| Train employees | Train 90% of project team members on AI-assisted development by Oct 2026 |

IT Project Management Lifecycle

A simple way to understand an IT project is:

1. Initiation
↓
2. Planning
↓
3. Execution
↓
4. Monitoring & Controlling
↓
5. Closing

Example: Mobile Banking Project

Initiation:
Why do we need the application?

↓

Planning:
What will we build? Who will build it? How much will it cost? When will it finish?

↓

Execution:
Develop and test the application.

↓

Monitoring & Controlling:
Track scope, schedule, cost, quality, risks, and issues.

↓

Closing:
Deploy, obtain acceptance, document lessons learned, and formally close the project.

Key Takeaway

A good IT Project Manager must continuously balance:

Scope + Time + Cost + Quality + Resources + Risk + Stakeholders + Business Value

The ultimate objective is not simply to finish the project.

A successful IT project delivers the intended business value and satisfies the needs of its stakeholders.

Project Constraints and Triple Constraint

According to the traditional PMBOK approach, project constraints are factors that limit the options available to the project team and influence how the project can be planned and executed.

A project manager must balance these constraints because changing one constraint can affect the others.

Common Project Constraints

Traditionally, the three major project constraints are:

- Scope

- Time

- Cost

However, projects are also affected by other constraints such as:

- Quality

- Resources

- Risk

- Stakeholder expectations

- Technology

- Regulatory requirements

Project Triple Constraint

The Triple Constraint is commonly represented as:

The basic idea is:

You cannot change one major constraint without potentially affecting the others.

Scope

What is Scope?

Scope defines the work that must be performed and the deliverables that must be produced to achieve the project's objectives.

It answers:

What are we going to deliver?

Example

A project is to develop a mobile banking application.

Scope includes:

- Login

- Account balance

- Fund transfer

- Bill payment

- Transaction history

But it does not include:

- Stock trading

- Insurance

- Cryptocurrency

Those excluded features are outside the agreed project scope.

Time

Time represents the duration or schedule required to complete the project.

It answers:

When must the project be completed?

Example

The mobile banking application must be completed within:

9 months

The project has milestones such as:

Requirements     → 1 month

Design            → 1 month

Development       → 4 months

Testing           → 2 months

Deployment        → 1 month

──────────

9 months

Cost

Cost represents the budget and financial resources required to complete the project.

It answers:

How much will it cost?

Example

The project budget is:

$500,000

It may include:

- Employee salaries

- Infrastructure

- Software licenses

- Cloud services

- Testing tools

- Consultants

- Training

Example of Triple Constraint

Imagine a company wants to develop an e-commerce application.

Original project

Scope:
20 features

Time:
6 months

Cost:
$300,000

Quality:
Agreed quality standards

SCOPE

20 features

/\

/  \

/    \

/      \

/        \

▼          ▼

TIME        COST

6 months     $300K

Now the customer says:

"We need 10 additional features."

The scope has increased.

What can happen?

Option 1 – Increase Time

20 features → 30 features

Time: 6 → 8 months

Cost may remain approximately the same.

Option 2 – Increase Cost

Hire additional developers.

Time: Remains 6 months

Cost: $300K → $400K

Option 3 – Reduce Scope Elsewhere

Add the 10 new features but remove lower-priority features.

Time: 6 months
Cost: $300K

But the original scope has changed.

Option 4 – Reduce Quality

Try to complete everything within 6 months and $300K by reducing testing.

This is generally not a good project-management decision, because it can create defects, security problems, and customer dissatisfaction.

Real-Life Example: Construction Project

Suppose a company wants to build a hospital.

Original baseline

| Constraint | Target |
| --- | --- |
| Scope | 200-bed hospital |
| Time | 24 months |
| Cost | $50 million |
| Quality | Required building standards |

Now the sponsor says:

"Make it a 300-bed hospital but finish at the same time."

Impact

Scope ↑

Therefore, the project may require:

Cost ↑

and/or

Time ↑

SCOPE

200 → 300 beds

/\

/  \

/    \

▼      ▼

TIME      COST

↑          ↑

24 months   $50M+

The Project Manager must negotiate and determine what can realistically change.

Expanded Project Constraints

Modern project management recognizes that projects are influenced by more than just scope, time, and cost.

A commonly used expanded model includes:

SCOPE

│

▼

┌───────┐

TIME ───►│PROJECT│◄─── COST

└───────┘

│

┌─────────────┼─────────────┐

▼             ▼             ▼

QUALITY       RESOURCES       RISK

│

▼

STAKEHOLDERS

Important constraints

Scope – What will be delivered?

Schedule – When will it be delivered?

Cost – How much can we spend?

Quality – How well must it perform?

Resources – Who and what are available?

Risk – What uncertainties can affect the project?

Stakeholders – What expectations and requirements must be satisfied?

Triple Constraint Example in IT

Project: Hospital Management System

The customer initially requests:

- Patient registration

- Appointment management

- Billing

- Pharmacy

- Reports

Baseline

Scope: 5 major modules
Time: 8 months
Cost: $400,000

After 4 months, the customer requests:

"Add an AI diagnosis assistant."

This is a scope change.

The Project Manager should evaluate its impact on:

- Scope

- Schedule

- Cost

- Resources

- Risk

- Quality

- Security

- Compliance

The PM should not simply tell the development team to add it.

Instead:

Change request → Impact analysis → Stakeholder decision → Update baselines/plans → Implement approved change

The Most Important Concept

The Triple Constraint teaches us that project constraints are interdependent.

Scope increases

➡️ Usually requires more time and/or cost

Time decreases

➡️ May require more resources/cost or reduced scope

Cost decreases

➡️ May require reduced scope, extended time, or different resources

1. Initiation Phase

What is it?

The Initiation Phase formally starts the project. The organization determines why the project is needed, whether it is feasible, what the high-level objectives are, and who the stakeholders are.

Main purpose

- Identify the business need

- Define the project at a high level

- Identify key stakeholders

- Obtain authorization to start the project

- Appoint/identify the Project Manager

Key PMBOK Processes

- Develop Project Charter

- Identify Stakeholders

Inputs → Tools & Techniques → Outputs

| Process | Inputs | Tools & Techniques | Outputs |
| --- | --- | --- | --- |
| Develop Project Charter | Business documents, agreements, EEFs, OPAs | Expert judgment, data gathering, interpersonal/team skills, meetings | Project Charter |
| Identify Stakeholders | Project Charter, business documents, project management plan, project documents, agreements, EEFs, OPAs | Expert judgment, data gathering, data analysis, decision making, data representation, meetings | Stakeholder Register |

Important Inputs

Business Case

- Explains why the project should be undertaken.

- Contains benefits, costs, risks, alternatives, and justification.

Project Statement of Work (SOW)

- Describes the product, service, or result that the project will deliver.

Enterprise Environmental Factors (EEFs)

- Conditions outside the project team's control.

- Example: government regulations, organizational culture, market conditions.

Organizational Process Assets (OPAs)

- Existing organizational knowledge and resources.

- Example: templates, policies, procedures, historical project data.

Main Outputs

Project Charter
Authorizes the project and gives the Project Manager authority to use organizational resources.

It generally contains:

- Project purpose

- Objectives

- High-level scope

- Major deliverables

- High-level requirements

- Key stakeholders

- Major risks

- Assumptions

- Constraints

- Milestones

- Budget summary

- Project Manager's authority

Stakeholder Register
Records:

- Who the stakeholders are

- Their roles

- Interests

- Influence

- Expectations

- Impact on the project

Simple Example

Project: Develop an Online Hospital Appointment System

Initiation determines:

"The hospital needs an online appointment system to reduce patient waiting time and improve appointment management."

The project charter authorizes the project, and the stakeholder register identifies hospital management, doctors, patients, IT team, QA team, and government/regulatory bodies.

2. Planning Phase

What is it?

Planning determines exactly how the project will be executed, monitored, controlled, and completed.

This is generally the most detailed phase because the project team develops the project management plan and supporting plans.

Main purpose

- Define detailed scope

- Create WBS

- Estimate resources, time, and cost

- Develop schedule

- Develop budget

- Identify and plan responses to risks

- Plan quality

- Plan communication

- Plan stakeholder engagement

- Plan procurement

- Establish baselines

Major PMBOK Planning Processes

Examples include:

- Develop Project Management Plan

- Plan Scope Management

- Collect Requirements

- Define Scope

- Create WBS

- Plan Schedule Management

- Define Activities

- Sequence Activities

- Estimate Activity Durations

- Develop Schedule

- Plan Cost Management

- Estimate Costs

- Determine Budget

- Plan Quality Management

- Plan Resource Management

- Plan Communications Management

- Plan Risk Management

- Identify Risks

- Perform Qualitative Risk Analysis

- Perform Quantitative Risk Analysis

- Plan Risk Responses

- Plan Procurement Management

- Plan Stakeholder Engagement

Inputs → Tools & Techniques → Outputs

Because Planning contains many processes, its ITTOs are extensive. At a high level:

| Planning Area | Typical Inputs | Tools & Techniques | Major Outputs |
| --- | --- | --- | --- |
| Scope | Charter, requirements, stakeholder information | Expert judgment, product analysis, decomposition | Scope Management Plan, Requirements, Scope Statement, WBS |
| Schedule | Scope, activities, resources | Critical Path Method, PERT, network analysis | Schedule Management Plan, Schedule, Schedule Baseline |
| Cost | Scope, schedule, resources | Analogous/parametric estimation, bottom-up estimation | Cost Estimates, Budget, Cost Baseline |
| Quality | Requirements, scope, organizational policies | Cost-benefit analysis, quality planning | Quality Management Plan |
| Resources | Scope, schedule, requirements | Organizational charts, RACI, expert judgment | Resource Management Plan |
| Risk | Scope, assumptions, stakeholder information | Risk identification, qualitative/quantitative analysis | Risk Register, Risk Responses |
| Communication | Stakeholder information | Communication requirements analysis | Communications Management Plan |
| Procurement | Scope, requirements, market conditions | Make-or-buy analysis, market research | Procurement Management Plan |
| Stakeholders | Stakeholder register | Engagement assessment | Stakeholder Engagement Plan |

Most Important Output: Project Management Plan

The Project Management Plan integrates all subsidiary plans and baselines.

It may include:

- Scope Management Plan

- Schedule Management Plan

- Cost Management Plan

- Quality Management Plan

- Resource Management Plan

- Communications Management Plan

- Risk Management Plan

- Procurement Management Plan

- Stakeholder Engagement Plan

- Requirements Management Plan

- Change Management Plan

- Configuration Management Plan

And baselines such as:

Scope Baseline + Schedule Baseline + Cost Baseline

Together, these form the Performance Measurement Baseline.

WBS – Important Planning Output

WBS = Work Breakdown Structure

It breaks the project scope into smaller, manageable components.

Example:

Online Hospital Appointment System

│

├── 1. Requirements

│   ├── 1.1 Patient Requirements

│   └── 1.2 Doctor Requirements

│

├── 2. Design

│   ├── 2.1 UI Design

│   └── 2.2 Database Design

│

├── 3. Development

│   ├── 3.1 Patient Module

│   ├── 3.2 Doctor Module

│   └── 3.3 Admin Module

│

├── 4. Testing

│   ├── 4.1 Functional Testing

│   └── 4.2 Performance Testing

│

└── 5. Deployment

The lowest level of the WBS contains work packages.

3. Execution Phase

What is it?

Execution is where the project team performs the work defined in the project management plan and creates the project's deliverables.

In simple terms:

Planning says what and how; Execution actually does it.

Main purpose

- Perform project work

- Create deliverables

- Manage project team

- Manage resources

- Perform quality assurance

- Communicate with stakeholders

- Implement risk responses

- Conduct procurements

- Manage knowledge

Key PMBOK Processes

Examples:

- Direct and Manage Project Work

- Manage Project Knowledge

- Manage Quality

- Acquire Resources

- Develop Team

- Manage Team

- Manage Communications

- Implement Risk Responses

- Conduct Procurements

- Manage Stakeholder Engagement

Inputs → Tools & Techniques → Outputs

| Process Area | Inputs | Tools & Techniques | Outputs |
| --- | --- | --- | --- |
| Direct & Manage Work | Project Management Plan, Project Documents | Expert judgment, PMIS, meetings | Deliverables, Work Performance Data |
| Manage Quality | Quality Management Plan, Quality Metrics | Quality audits, problem solving, quality improvement | Quality Reports, Test & Evaluation Documents |
| Acquire Resources | Resource Management Plan | Negotiation, decision making | Physical/Team Resources |
| Develop Team | Resource Management Plan | Team building, training, recognition | Team Performance Assessments |
| Manage Team | Team performance data | Conflict management, decision making | Change Requests, Project Management Plan Updates |
| Manage Communications | Communications Plan | Communication methods, PMIS | Project Communications |
| Implement Risk Responses | Risk Register, Risk Plan | Expert judgment, risk response strategies | Change Requests, Issue Updates |
| Conduct Procurements | Procurement Plan, Bid Documents | Bidder conferences, proposal evaluation, negotiation | Selected Sellers, Agreements |
| Manage Stakeholder Engagement | Stakeholder Engagement Plan | Communication, interpersonal skills | Change Requests, Project Management Plan Updates |

Major Outputs

Deliverables

- The actual products/services/results produced by the project.

Work Performance Data

- Raw observations and measurements.

- Example:

  - 15 tasks completed

  - 3 defects found

  - 80 hours spent

Change Requests

- Requests to modify scope, schedule, cost, quality, etc.

Example

For the hospital appointment system:

During execution:

- Developers develop the application.

- QA tests it.

- Database team creates databases.

- UI team develops interfaces.

- Project manager coordinates the team.

- Risks are addressed.

- Stakeholders receive project updates.

4. Monitoring & Controlling Phase

What is it?

Monitoring and Controlling happens throughout the project, alongside Execution.

It answers:

"Are we doing what we planned, and if not, what corrective action should we take?"

This phase is not performed only after execution.

Main purpose

- Monitor project performance

- Compare actual performance with baselines

- Identify deviations

- Control scope

- Control schedule

- Control cost

- Control quality

- Monitor risks

- Control changes

- Monitor stakeholder engagement

- Take corrective/preventive action

Key PMBOK Processes

Examples:

- Monitor and Control Project Work

- Perform Integrated Change Control

- Validate Scope

- Control Scope

- Control Schedule

- Control Costs

- Control Quality

- Monitor Communications

- Monitor Risks

- Control Procurements

- Monitor Stakeholder Engagement

Inputs → Tools & Techniques → Outputs

| Process | Inputs | Tools & Techniques | Outputs |
| --- | --- | --- | --- |
| Monitor & Control Work | Project Management Plan, Project Documents, Work Performance Data | Expert judgment, data analysis, decision making | Work Performance Reports, Change Requests |
| Integrated Change Control | Project Management Plan, Change Requests, Work Performance Reports | Change control tools, decision making, meetings | Approved/Rejected Change Requests, Plan Updates |
| Validate Scope | Scope Baseline, Requirements, Verified Deliverables | Inspection, decision making | Accepted Deliverables, Change Requests |
| Control Scope | Scope Baseline, Requirements | Variance analysis, trend analysis | Work Performance Information, Change Requests |
| Control Schedule | Schedule Baseline, Project Schedule | Critical Path Method, trend analysis, EVM | Schedule Forecasts, Change Requests |
| Control Costs | Cost Baseline, Cost Data | Earned Value Management, variance analysis | Cost Forecasts, Change Requests |
| Control Quality | Quality Metrics, Test Results | Inspection, testing, data analysis | Verified Deliverables, Quality Reports |
| Monitor Risks | Risk Register, Issue Log | Risk reassessment, audits, data analysis | Risk Updates, Change Requests |

Key Concept: Performance Comparison

The project manager compares:

Planned vs Actual

For example:

| Metric | Planned | Actual | Status |
| --- | --- | --- | --- |
| Schedule | 60 days | 68 days | ⚠️ Delayed |
| Budget | $100,000 | $108,000 | ⚠️ Over budget |
| Defects | <20 | 12 | ✅ Good |
| Scope | 100% | 100% | ✅ Good |

The Project Manager then determines whether corrective or preventive action is required.

5. Closing Phase

What is it?

Closing formally completes the project or a project phase.

The project is not considered complete simply because the product has been developed.

The project must be formally closed and accepted.

Main purpose

- Obtain formal acceptance

- Complete all project work

- Close contracts

- Archive documents

- Release resources

- Capture lessons learned

- Transition the product/service

- Formally close the project

Key PMBOK Process

Close Project or Phase

Inputs → Tools & Techniques → Outputs

| Process | Inputs | Tools & Techniques | Outputs |
| --- | --- | --- | --- |
| Close Project or Phase | Project Charter, Project Management Plan, Project Documents, Accepted Deliverables, Business Documents, Agreements, Procurement Documents | Expert judgment, data analysis, meetings | Final Product/Service/Result Transition, Final Report, Organizational Process Asset Updates |

Major Outputs

1. Final Product/Service/Result Transition

- Product is handed over to operations/customer.

2. Final Report
Contains overall project performance such as:

- Scope achieved

- Schedule performance

- Cost performance

- Quality performance

- Major risks/issues

- Lessons learned

3. Lessons Learned
Documents:

- What went well?

- What went wrong?

- What should be repeated?

- What should be avoided?

4. Organizational Process Asset Updates
The organization updates its knowledge repository with:

- Lessons learned

- Templates

- Historical information

- Project records

Example

For the hospital appointment system:

- Hospital formally accepts the system.

- System is transferred to the operations/support team.

- Contracts are closed.

- Project documents are archived.

- Project team members are released.

- Final report is prepared.

- Lessons learned are documented.

Complete 5-Phase Flow

PROJECT

│

▼

┌─────────────────────┐

│ 1. INITIATION       │

│ Why do we do it?    │

└──────────┬──────────┘

│

▼

┌─────────────────────┐

│ 2. PLANNING         │

│ How will we do it?  │

└──────────┬──────────┘

│

▼

┌─────────────────────┐

│ 3. EXECUTION        │

│ Do the work         │

└──────────┬──────────┘

│

▼

┌──────────────────────────┐

│ 4. MONITOR & CONTROL     │

│ Are we on track?         │

└──────────┬───────────────┘

│

Corrective/

Preventive Action

│

└──────► Execution

│

▼

┌─────────────────────┐

│ 5. CLOSING          │

│ Formally finish     │

└─────────────────────┘

Quick ITTO Summary

| Phase | Key Inputs | Key Tools & Techniques | Key Outputs |
| --- | --- | --- | --- |
| Initiation | SOW, Business Case, Agreements, EEFs, OPAs | Expert Judgment, Data Gathering, Meetings | Project Charter, Stakeholder Register |
| Planning | Charter, Requirements, Stakeholder Register, EEFs, OPAs | Expert Judgment, Decomposition, Estimation, CPM, PERT, Risk Analysis | Project Management Plan, WBS, Schedule, Budget, Risk Register, Baselines |
| Execution | Project Management Plan, Project Documents | Expert Judgment, PMIS, Team Skills, Meetings | Deliverables, Work Performance Data, Change Requests, Project Updates |
| Monitoring & Controlling | Plan, Baselines, Work Performance Data, Project Documents | Variance Analysis, Trend Analysis, EVM, Inspection, Audits, CPM | Work Performance Information, Reports, Forecasts, Change Requests, Approved Changes |
| Closing | Project Plan, Accepted Deliverables, Project Documents, Agreements | Expert Judgment, Data Analysis, Meetings | Final Product/Service, Final Report, Lessons Learned, OPA Updates |

Easy way to remember

Initiation → PLANNING → EXECUTION → MONITOR & CONTROL → CLOSING

Initiation: Why?
Planning: What, how, when, who, and how much?
Execution: Do it.
Monitoring & Controlling: Check it and correct it.
Closing: Accept it, hand it over, and formally finish it.