PROJECT PLANNING

Project planning is the process of defining how a project will be executed, monitored, and controlled.

It answers:

- What work will be done? (Scope)

- When will it be done? (Schedule)

- How much will it cost? (Cost)

- How will work be broken down? (WBS)

PROJECT SCOPE PLANNING

Project scope defines:

All the work required—and only the work required—to complete the project successfully.

It prevents scope creep (uncontrolled changes).

Scope Planning Includes

- Collecting requirements

- Defining project boundaries

- Creating scope statement

- Defining deliverables

- Acceptance criteria

Output: Scope Statement

Example: Online Food Delivery App

In Scope:

- User registration/login

- Restaurant listing

- Food ordering system

- Payment gateway integration

- Order tracking

Out of Scope:

- Restaurant inventory management

- Delivery driver payroll system

- AI food recommendation system (Phase 2)

Example (Simple)

If building a Library Management System, scope includes:

- Book issuing/return

- User database

- Fine calculation

NOT included:

- Online bookstore selling feature

PROJECT WBS (WORK BREAKDOWN STRUCTURE)

WBS is:

A hierarchical breakdown of total project work into smaller manageable tasks

It organizes work into deliverable-based chunks.

Why WBS is Important

- Makes project easy to manage

- Improves estimation (time & cost)

- Assigns responsibilities clearly

- Helps track progress

WBS Structure Example

Level 1: Project

- FoodExpress App Development

Level 2: Major Deliverables

- UI/UX Design

- Frontend Development

- Backend Development

- Database Design

- Testing

- Deployment

Level 3: Breakdown

1. UI/UX Design

- Wireframes

- Prototypes

- User flow design

2. Backend Development

- User authentication module

- Order management API

- Payment integration API

Example (Real-world analogy)

Building a house:

- Foundation

- Walls

- Roof

- Electrical work

Same idea in software → modules/components

PROJECT SCHEDULE PLANNING

Project scheduling defines:

When each task will start and finish

It converts WBS into a timeline.

Tools Used

- Gantt Chart

- Network Diagram (PERT/CPM)

- Milestone chart

Example Schedule

| Task | Duration | Start | End |
| --- | --- | --- | --- |
| Requirement Gathering | 1 week | Week 1 | Week 1 |
| UI Design | 2 weeks | Week 2 | Week 3 |
| Backend Development | 4 weeks | Week 3 | Week 6 |
| Frontend Development | 4 weeks | Week 3 | Week 6 |
| Testing | 2 weeks | Week 7 | Week 8 |
| Deployment | 1 week | Week 9 | Week 9 |

Milestones Example

- Requirements completed ✔

- UI approved ✔

- MVP ready ✔

- System deployed ✔

Simple Explanation

Schedule = WBS + Time

PROJECT COST PLANNING

Cost planning estimates:

Total money required to complete the project

Cost Includes

- Human resources (salary)

- Software/tools

- Hardware

- Cloud hosting

- Testing tools

- Contingency reserve (risk buffer)

Example Cost Estimation

| Cost Component | Estimated Cost |
| --- | --- |
| Project Manager | $5,000 |
| Developers (4 people) | $20,000 |
| UI/UX Designer | $3,000 |
| Cloud Hosting (AWS) | $2,000 |
| Testing Tools | $1,000 |
| Miscellaneous | $2,000 |
| Total | $33,000 |

Cost Estimation Methods

- Analogous estimation (past project comparison)

- Bottom-up estimation (WBS-based)

- Parametric estimation (cost per module)

Example Insight

If backend takes more effort → cost increases due to developer time.

HOW ALL ARE CONNECTED

Project Planning Flow:

Scope → WBS → Schedule → Cost

Simple Explanation:

- Scope = What to build

- WBS = Breakdown of work

- Schedule = When to build

- Cost = How much it will cost

FINAL EXAMPLE

Project: Online Food Delivery App

- Scope: ordering, payments, tracking

- WBS: UI, backend, database, testing

- Schedule: 9-week plan

- Cost: $33,000

QUICK REVISION POINTS

- Scope = project boundaries

- WBS = breakdown of tasks

- Schedule = timeline of tasks

- Cost = budget estimation

Planning Phase

The Project Planning Phase is the second phase of the project life cycle, where the project team defines how the project will be executed, monitored, and controlled. It converts the high-level idea from the Initiation phase into a clear, actionable roadmap.

The Project Planning Phase is the process of:

- Defining project scope in detail

- Creating schedules, budgets, and resource plans

- Identifying risks and mitigation strategies

- Establishing communication and quality plans

Simple meaning:

“Planning phase decides HOW the project will be done.”

Why Planning Phase is Important?

✔ Clear Direction

Avoids confusion during execution.

✔ Reduces Risks

Identifies risks early.

✔  Better Resource Management

Ensures right people, time, and budget.

✔ 4. Improves Success Rate

Well-planned projects are more likely to succeed.

✔ Baseline for Execution

Acts as reference for monitoring progress.

Project Planning Phase — Key Inputs, Tools, Outputs

Inputs (What you need before planning)

Project Charter

- High-level project approval document

- Defines goals, scope, and sponsor

Stakeholder Register

- Identifies stakeholders and their needs

EEF (Enterprise Environmental Factors)

External/internal conditions like:

- Company culture

- Market conditions

- Legal rules

- Technology environment

OPA (Organizational Process Assets)

Internal company resources:

- Templates

- Policies

- Past project data

- Lessons learned

Tools & Techniques (How planning is done)

Expert Judgment

- Experienced managers guide planning

Brainstorming

- Generate ideas and solutions

Meetings & Workshops

- Team discussions for scope, risks, etc.

Work Breakdown Structure (WBS)

- Breaking project into smaller tasks

A Work Breakdown Structure (WBS) is a hierarchical decomposition of the total project work into smaller, manageable components. It helps the project team organize and define all the work needed to complete the project successfully.

A Work Breakdown Structure (WBS) is a deliverable-oriented hierarchical breakdown of the work to be executed by the project team.

“Breaking a large project into smaller tasks until the work becomes easy to manage.”

Why WBS is Important?

✔ Better Project Organization

Large projects become manageable.

✔ Easier Task Assignment

Each task can be assigned to specific team members.

✔ Better Time & Cost Estimation

Smaller tasks are easier to estimate.

✔ Improves Tracking & Monitoring

Progress can be tracked at each level.

✔ Reduces Missing Work

Ensures all project work is identified.

Key Characteristics of WBS

| Characteristic | Description |
| --- | --- |
| Hierarchical | Organized in levels |
| Deliverable-oriented | Focuses on outputs |
| Decomposition | Breaks work into smaller pieces |
| 100% Rule | Includes all project work |
| Manageable Units | Small enough to estimate and control |

WBS Hierarchy Levels

A WBS is usually divided into levels:

| Level | Description |
| --- | --- |
| Level 1 | Project |
| Level 2 | Major Deliverables |
| Level 3 | Sub-deliverables |
| Level 4 | Work Packages |

What is a Work Package?

The lowest level of WBS is called a Work Package.

It is:

- Small enough to estimate

- Assignable to one person/team

- Trackable and measurable

Example of WBS (IT Project)

roject: Online Food Delivery System

1. Online Food Delivery System
│
├── 1.1 Requirement Analysis
│   ├── 1.1.1 Gather Requirements
│   ├── 1.1.2 Stakeholder Meetings
│   └── 1.1.3 Requirement Documentation
│
├── 1.2 System Design
│   ├── 1.2.1 UI/UX Design
│   ├── 1.2.2 Database Design
│   └── 1.2.3 Architecture Design
│
├── 1.3 Development
│   ├── 1.3.1 Frontend Development
│   ├── 1.3.2 Backend Development
│   ├── 1.3.3 API Integration
│   └── 1.3.4 Payment Gateway Integration
│
├── 1.4 Testing
│   ├── 1.4.1 Unit Testing
│   ├── 1.4.2 Integration Testing
│   ├── 1.4.3 System Testing
│   └── 1.4.4 User Acceptance Testing
│
└── 1.5 Deployment
    ├── 1.5.1 Server Setup
    ├── 1.5.2 Production Deployment
    └── 1.5.3 User Training

Visual WBS Diagram

Online Food Delivery System
                               │
 ┌───────────────┬───────────────┬───────────────┬───────────────┐
 Requirement     Design        Development       Testing      Deployment
 Analysis

Advantages of WBS

✔ Better planning
✔ Accurate estimation
✔ Easier tracking
✔ Improved communication
✔ Better risk identification

Simple Summary

WBS is:

✔ A hierarchical breakdown of project work
✔ Used to organize and manage project tasks
✔ Helps in estimation, scheduling, and monitoring
✔ Ends with manageable work packages

Scheduling Tools

- Gantt charts

- Critical Path Method (CPM)

Estimation Techniques

- Analogous estimation

- Parametric estimation

- Bottom-up estimation

Risk Analysis Tools

- SWOT analysis

- Risk probability & impact matrix

A Risk Probability and Impact Matrix is a project risk management tool used to:

- Evaluate project risks

- Prioritize risks

- Decide which risks need immediate attention

It helps the project team understand:

“Which risks are most dangerous to the project?”

What is Risk Probability & Impact Matrix?

It is a grid/table that measures risks based on:

- Probability → How likely the risk is to happen

- Impact → How severe the effect will be if it happens

The combination determines the risk severity level.

Why is it Needed?

✔ Prioritize Risks

Not all risks are equally important.

✔ Better Decision Making

Focus resources on high-priority risks.

✔ Improves Risk Response Planning

Helps decide mitigation actions.

✔ Reduces Project Failure Chances

Early identification prevents major problems.

Key Concepts

Probability

Probability means:

“Chance that the risk will occur”

Usually expressed as:

- Percentage

- Scale (1–5)

Example Probability Scale

| Score | Probability | Meaning |
| --- | --- | --- |
| 1 | Very Low | Rare |
| 2 | Low | Unlikely |
| 3 | Medium | Possible |
| 4 | High | Likely |
| 5 | Very High | Almost certain |

Impact

Impact means:

“How much damage the risk can cause”

Can affect:

- Cost

- Schedule

- Quality

- Scope

- Security

Example Impact Scale

| Score | Impact | Meaning |
| --- | --- | --- |
| 1 | Very Low | Minimal effect |
| 2 | Low | Small delay/cost |
| 3 | Medium | Noticeable issue |
| 4 | High | Serious problem |
| 5 | Very High | Project failure possible |

Risk Score Formula

Many organizations calculate:

Risk Score=Probability×Impact

Detailed IT Project Example

Project: Online Banking Application

Step 1: Identify Risks

| Risk ID | Risk Description |
| --- | --- |
| R1 | Cybersecurity attack |
| R2 | Developer resignation |
| R3 | Delay in API integration |
| R4 | Server outage |
| R5 | Requirement changes |

Step 2: Assign Probability & Impact

| Risk | Probability | Impact |
| --- | --- | --- |
| Cybersecurity attack | 4 | 5 |
| Developer resignation | 3 | 3 |
| API delay | 4 | 4 |
| Server outage | 2 | 5 |
| Requirement changes | 5 | 3 |

Step 3: Calculate Risk Score

| Risk | Probability | Impact | Score |
| --- | --- | --- | --- |
| Cybersecurity attack | 4 | 5 | 20 |
| Developer resignation | 3 | 3 | 9 |
| API delay | 4 | 4 | 16 |
| Server outage | 2 | 5 | 10 |
| Requirement changes | 5 | 3 | 15 |

Step 4: Prioritize Risks

| Risk | Level | Action |
| --- | --- | --- |
| Cybersecurity attack | Critical | Immediate mitigation |
| API delay | Critical | Escalate & monitor daily |
| Requirement changes | High | Strong change control |
| Server outage | Medium | Backup server setup |
| Developer resignation | Medium | Cross-training |

Software Tools

- MS Project

- Jira

- Trello

Outputs (What you get after planning)

Project Management Plan (Main Output)

This is the master document containing:

- Scope management plan

- Schedule management plan

- Cost management plan

- Quality management plan

- Risk management plan

- Communication plan

- Resource plan

Scope Baseline

Includes:

- Project scope statement

- WBS

- WBS dictionary

Schedule Baseline

- Final approved timeline

Cost Baseline

- Approved budget plan

Risk Register

- List of risks and mitigation plans

Communication Plan

- Who gets what information, when, and how

Resource Management Plan

- Team roles and responsibilities

Example: IT Project Planning Phase

Project: Online Food Delivery App

Inputs

- Project Charter approved by CEO

- Stakeholder Register (customers, restaurants, dev team)

- Company policies (Agile methodology)

- Past mobile app project data

Planning Activities

Scope Planning

- Features:

  - User login

  - Order food

  - Payment integration

WBS Creation

- Level 1: Food Delivery App

  - Level 2: Frontend

  - Level 2: Backend

  - Level 2: Payment system

  - Level 2: Testing

Schedule Planning

- Design: 3 weeks

- Development: 3 months

- Testing: 1 month

Cost Estimation

- Total budget: $150,000

  - Developers: $80,000

  - Design: $20,000

  - Testing: $30,000

  - Marketing: $20,000

Risk Planning

| Risk | Mitigation |
| --- | --- |
| Payment gateway failure | Use backup provider |
| Delay in development | Add extra developers |
| Security breach | Use encryption & testing |

Communication Plan

- Weekly meetings with team

- Monthly report to CEO

- Daily standup (Agile)

Outputs

- Project Management Plan created

- WBS finalized

- Schedule baseline approved

- Cost baseline fixed

- Risk register created

Simple Summary

Project Planning Phase is:

✔ The roadmap of the project
✔ Defines what, how, when, and by whom work will be done
✔ Produces detailed documents like WBS, schedule, budget, risk plan

Here are detailed notes on estimation techniques used in project management and software engineering, focusing on:

- ✅ COCOMO model

- ✅ Agile estimation (Story Points, Planning Poker, T-shirt sizing)

- ✅ PERT estimation

Each includes clear explanation + formulas + real examples.

1. COCOMO (Constructive Cost Model)

What is COCOMO?

COCOMO is an algorithmic software cost estimation model developed by Barry Boehm.

It estimates:

- Effort (person-months)

- Development time

- Cost

It uses:

Size of software (KLOC = Kilo Lines of Code)

Types of COCOMO

1️⃣ Basic COCOMO

Uses only KLOC.

2️⃣ Intermediate COCOMO

Includes cost drivers (complexity, team capability, tools).

3️⃣ Detailed COCOMO

Breaks project into phases.

Basic COCOMO Formula

🔹 Effort (E):

E=a×(KLOC)b

🔹 Development Time (T):

T=c×(E)d

Project Types in COCOMO

| Type | Description | Example |
| --- | --- | --- |
| Organic | Small, simple systems | Student app |
| Semi-detached | Medium complexity | Banking system |
| Embedded | Complex, hardware-dependent | ATM system |

Example (COCOMO)

Project: Library Management System

Estimated size = 50 KLOC

Assume Organic type:

- a = 2.4, b = 1.05

Step 1: Effort

E=2.4×(50)1.05

≈ 2.4 × 63.1
≈ 151 person-months

Step 2: Time

T=2.5×(151)0.38

≈ 2.5 × 6.3
≈ 15.7 months

Interpretation

- 151 person-months = 10 developers ≈ 15 months

- Helps in budgeting and staffing

2. AGILE ESTIMATION

Agile estimation is used in Scrum / Agile projects where requirements evolve.

Instead of hours → we use relative estimation

Common Agile Techniques

1️⃣ Story Points

What is it?

Story points measure:

- Effort

- Complexity

- Risk

Not time directly.

Scale Example

| Story Points | Meaning |
| --- | --- |
| 1 | Very easy |
| 2 | Easy |
| 5 | Medium |
| 8 | Hard |
| 13 | Very complex |

Example

User Story: “Login with OTP”

Team decides:

- Simple UI → 2 points

- SMS API integration → 3 points
👉 Final: 5 Story Points

Velocity Concept

If team completes:

- 30 story points per sprint

Then:

- 100-point project ≈ 3–4 sprints

2️⃣ Planning Poker

What is it?

A team-based estimation technique

Process:

- Product Owner explains story

- Team discusses

- Everyone picks card (1,2,3,5,8…)

- Reveal simultaneously

- Discuss differences

- Final consensus

Example

User story: “Add payment gateway”

Votes:

- Dev A: 8

- Dev B: 13

- Dev C: 8

Final decision: 8 or 10 story points

Why it works

- Avoids bias

- Encourages discussion

- Better accuracy

T-SHIRT SIZING

What is it?

Simple high-level estimation:

| Size | Meaning |
| --- | --- |
| XS | Very small task |
| S | Small |
| M | Medium |
| L | Large |
| XL | Very large |

Example

For a Food Delivery App:

| Feature | Size |
| --- | --- |
| Login page | S |
| Payment integration | L |
| Real-time tracking | XL |

Use Case

- Early planning

- When requirements are unclear

3. PERT (Program Evaluation Review Technique)

What is PERT?

PERT is a statistical time estimation technique used when activity time is uncertain.

It uses 3 time estimates:

- Optimistic (O)

- Most likely (M)

- Pessimistic (P)

Formula

TE=O+4M+P6

Where:

- TE = Expected time

Example

Task: “Develop login module”

| Estimate | Days |
| --- | --- |
| Optimistic (O) | 2 days |
| Most likely (M) | 5 days |
| Pessimistic (P) | 11 days |

Calculation:

TE=(2+4(5)+11)/6
TE=(2+20+11)/6=33/6=5.5days

Interpretation

Even though worst case is 11 days, expected is 5.5 days

PERT Use Case

- Research projects

- New software development

- Uncertain environments

COMPARISON OF ALL TECHNIQUES

| Technique | Type | Best Used For | Output |
| --- | --- | --- | --- |
| COCOMO | Algorithmic | Large software systems | Cost, effort |
| Agile Estimation | Relative | Agile projects | Story points |
| PERT | Statistical | Uncertain tasks | Time estimate |

REAL-WORLD EXAMPLE (Combined Use)

Project: Food Delivery App

- COCOMO → Overall cost estimate = $50,000

- Agile → Sprint planning (story points = 120 total)

- PERT → Login module = 5.5 days expected time

FINAL SUMMARY

- COCOMO → predicts effort using code size

- Agile estimation → relative effort in story points

- PERT → probabilistic time estimation

Here are detailed, exam-ready notes on developing project schedules, focusing on:

- Gantt Charts

- Critical Path Method (CPM)

- With clear IT project examples and step-by-step explanation

PROJECT SCHEDULING (Overview)

What is Project Scheduling?

Project scheduling is the process of:

Defining the sequence of tasks, their duration, dependencies, and timeline for project completion.

It answers:

- What tasks are done?

- In what order?

- How long will each take?

- What is the project completion date?

GANTT CHART

What is a Gantt Chart?

A Gantt chart is:

A horizontal bar chart that shows project tasks against time.

It visually represents:

- Tasks

- Start and end dates

- Duration

- Progress

Key Components

- Tasks (Y-axis)

- Time scale (X-axis)

- Bars (duration of tasks)

- Milestones (important checkpoints)

- Dependencies (links between tasks)

Example: Online Food Delivery App

Project Tasks

| Task | Duration |
| --- | --- |
| Requirement Gathering | 2 days |
| UI Design | 4 days |
| Backend Development | 6 days |
| Frontend Development | 6 days |
| Testing | 3 days |
| Deployment | 1 day |

Gantt Chart Representation (Text View)

Day → 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20

Requirement  █ █
UI Design          █ █ █ █
Backend                █ █ █ █ █ █
Frontend               █ █ █ █ █ █
Testing                               █ █ █
Deployment                                      █

Advantages of Gantt Chart

- Easy to understand visually

- Shows progress clearly

- Helps in tracking delays

- Useful for reporting to stakeholders

Limitations

- Difficult for very large projects

- Does not clearly show complex dependencies

- Hard to update manually

Real-world Use

- Software development projects

- Construction projects

- Product launches

2. CRITICAL PATH METHOD (CPM)

What is CPM?

Critical Path Method is:

A technique used to find the longest sequence of dependent tasks that determines the minimum project duration.

👉 The critical path = the shortest possible time to complete the project

Key Concepts

1. Activities

Tasks in the project

2. Dependencies

Some tasks must finish before others start

3. Duration

Time required for each task

4. Critical Path

Longest path through the network

CPM EXAMPLE (Step-by-Step)

Project: Website Development

Activities

| Task | Duration | Dependency |
| --- | --- | --- |
| A: Requirements | 2 days | Start |
| B: UI Design | 3 days | A |
| C: Backend Setup | 4 days | A |
| D: Frontend Dev | 3 days | B |
| E: Integration | 2 days | C, D |
| F: Testing | 2 days | E |

Step 1: Draw Paths

Path 1:

A → B → D → E → F
= 2 + 3 + 3 + 2 + 2 = 12 days

Path 2:

A → C → E → F
= 2 + 4 + 2 + 2 = 10 days

Step 2: Identify Critical Path

Longest path = 12 days

Critical Path:

A → B → D → E → F

Step 3: Interpretation

- Project duration = 12 days

- Any delay in critical path = project delay

- Tasks on non-critical path have flexibility

CPM Diagram (Text Form)

Start
  |
  A (2)
 / \
B   C
(3) (4)
 |    |
 D    |
(3)   |
  \  /
   E (2)
    |
   F (2)
    |
  End

Key Terms in CPM

1. Float / Slack

Extra time a task can be delayed without affecting project

- Critical path tasks → Zero float

- Non-critical tasks → Have float

2. Early Start (ES)

Earliest time task can begin

3. Late Finish (LF)

Latest time task can finish without delay

Advantages of CPM

- Identifies project duration accurately

- Highlights critical tasks

- Helps in resource allocation

- Useful for complex projects

Limitations of CPM

- Time estimates must be accurate

- Complex for large projects

- Does not handle uncertainty (use PERT instead)

GANTT CHART vs CPM

| Feature | Gantt Chart | CPM |
| --- | --- | --- |
| Representation | Bar chart | Network diagram |
| Focus | Timeline | Dependencies |
| Best for | Simple tracking | Complex scheduling |
| Critical path | Not visible clearly | Clearly identified |
| Flexibility | Medium | High |

REAL-LIFE EXAMPLE (Combined)

Project: Food Delivery App

Gantt Chart Use:

- Visual timeline for UI, backend, testing

CPM Use:

- Identify critical path:
Requirements → Backend → Integration → Testing

This ensures:

- No delay in backend = no delay in project

FINAL SUMMARY

- 📊 Gantt Chart → Visual timeline of tasks

- 🔗 CPM → Finds longest dependent task path

- ⚠️ Critical Path → Determines project duration

- ⏱️ Slack → Delay allowed for non-critical tasks

PROJECT COST MANAGEMENT (Overview)

What is Cost Management?

Project Cost Management is the process of:

Estimating, budgeting, and controlling costs so that the project is completed within the approved budget.

It ensures:

- No overspending

- Proper allocation of funds

- Financial control throughout the project lifecycle

Main Processes in Cost Management

- Cost Estimation → How much will it cost?

- Cost Budgeting → How will cost be distributed?

- Cost Control → How to manage spending during execution?

1. COST ESTIMATION

Cost estimation is:

Predicting the total cost of a project before execution begins.

It includes:

- Labor cost

- Software/tools

- Hardware

- Cloud services

- Testing

- Risk reserve

Types of Cost Estimation Techniques

1️⃣ Analogous Estimation

Uses cost of similar past projects

✔ Fast but less accurate

Example:

- Previous food delivery app cost = $40,000

- New similar app → estimated = $45,000

2️⃣ Bottom-Up Estimation

Cost is calculated from WBS level tasks

Most accurate

Example (Food App):

| Task | Cost |
| --- | --- |
| UI Design | $5,000 |
| Backend | $15,000 |
| Testing | $6,000 |
| Deployment | $2,000 |
| Total | $28,000 |

3️⃣ Parametric Estimation

Uses mathematical relationship (cost per unit)

Formula:
Cost = Cost per unit × quantity

Example:

- $50 per developer hour

- 400 hours required
= $20,000

4️⃣ Expert Judgment

Based on experienced project managers

✔ Quick but subjective

2. PROJECT BUDGETING

Project budgeting is:

Allocating estimated costs to different project activities over time.

It converts:
Cost estimates → time-based financial plan

Purpose of Budgeting

- Control spending

- Plan cash flow

- Track performance

- Avoid financial risk

Example: Food Delivery App Budget

Total Estimated Cost = $50,000

| Phase | Budget Allocation |
| --- | --- |
| Planning | $5,000 |
| Design | $8,000 |
| Development | $25,000 |
| Testing | $7,000 |
| Deployment | $3,000 |
| Contingency | $2,000 |
| Total | $50,000 |

Budget Timeline View

| Month | Spending |
| --- | --- |
| Month 1 | $10,000 |
| Month 2 | $15,000 |
| Month 3 | $20,000 |
| Month 4 | $5,000 |

Key Output: Cost Baseline

Approved budget used as a reference for tracking project performance

3. COST CONTROL

Cost control is:

Monitoring and managing project expenses to ensure they stay within the budget.

Activities in Cost Control

- Tracking actual costs

- Comparing with budget

- Managing variances

- Preventing overspending

- Forecasting future costs

Earned Value Management (EVM)

EVM is a powerful cost control technique.

Key Terms

1️⃣ Planned Value (PV)

Budgeted cost of work planned

2️⃣ Earned Value (EV)

Budgeted cost of work completed

3️⃣ Actual Cost (AC)

Real money spent

Example

Project Budget = $100,000

- PV = $50,000 (planned work)

- EV = $40,000 (work completed)

- AC = $60,000 (actual spending)

Cost Variance (CV)

CV=EV-AC
CV=40,000-60,000=-20,000

👉 Negative = Over budget ❌

Schedule Variance (SV)

SV=EV-PV
SV=40,000-50,000=-10,000

👉 Behind schedule ❌

Cost Performance Index (CPI)

CPI=EVAC
CPI=40,000/60,000=0.67

👉 CPI < 1 = inefficient spending

Simple Interpretation

| Metric | Result | Meaning |
| --- | --- | --- |
| CV | Negative | Over budget |
| SV | Negative | Delay |
| CPI | < 1 | Poor cost efficiency |

Example: IT Project Scenario

Project: Mobile Banking App

| Item | Cost |
| --- | --- |
| Budget | $80,000 |
| Spent so far | $50,000 |
| Work completed value | $40,000 |

👉 Problem:

- Spending faster than progress

- Risk of budget overrun

Budget vs Cost Control

| Budgeting | Cost Control |
| --- | --- |
| Planning stage | Execution stage |
| Estimates cost | Tracks cost |
| Sets baseline | Ensures compliance |

Reserve Analysis

Types of reserves:

1️⃣ Contingency Reserve

- For known risks

- Example: delay in API integration

2️⃣ Management Reserve

- For unknown risks

- Example: sudden tech change

Cost Management Flow

Estimation → Budgeting → Baseline → Execution → Cost Control

REAL-WORLD EXAMPLE (FULL FLOW)

Project: Food Delivery App

1. Estimation

- Total cost = $50,000

2. Budgeting

- Development = $25,000

- Testing = $7,000

3. Execution

- Actual spent = $30,000

4. Control

- EV = $25,000

- AC = $30,000
👉 Over budget situation

FINAL SUMMARY

- Cost Estimation → Predict cost

- Budgeting → Allocate cost over time

- Cost Control → Monitor & adjust spending

- EVM → Measure project performance

Project Planning as per PMBOK

1. What is Project Planning?

Project Planning is the process of deciding what needs to be done, how it will be done, who will do it, when it will be done, and how much it will cost to successfully complete a project.

In simple words:

Project Planning = Scope + Work + Resources + Time + Cost + Risk + Quality + Communication

Example

For an Online Shopping Application:

- What? → Develop an e-commerce application

- How? → Requirements → Design → Development → Testing → Deployment

- Who? → Developers, QA, UI/UX, Project Manager

- When? → 6 months

- How much? → $100,000

- Risks? → Requirement changes, technical issues, security problems

2. Project Planning Steps as per PMBOK

PMBOK treats planning as a collection of processes used to develop the Project Management Plan and subsidiary plans.

Major Planning Steps

Project Charter

↓

Define Scope

↓

Create WBS

↓

Define Activities

↓

Sequence Activities

↓

Estimate Resources & Duration

↓

Develop Schedule

↓

Estimate Costs

↓

Determine Budget

↓

Plan Quality

↓

Plan Resources

↓

Plan Communications

↓

Plan Risk Management

↓

Plan Procurement

↓

Plan Stakeholder Engagement

↓

Project Management Plan

Key outputs include:

- Scope Management Plan

- Schedule Management Plan

- Cost Management Plan

- Quality Management Plan

- Resource Management Plan

- Communications Management Plan

- Risk Management Plan

- Procurement Management Plan

- Stakeholder Engagement Plan

- Project Management Plan

3. What is WBS?

WBS = Work Breakdown Structure

WBS is a hierarchical decomposition of the total project scope into smaller, manageable components called work packages.

Simple definition

WBS breaks a large project into smaller pieces of work that are easier to estimate, assign, schedule and control.

Important point

WBS focuses on WHAT work needs to be done, not WHEN it will be done.

Example: E-Commerce Website WBS

1. E-Commerce Website

│

├── 1.1 Project Management

│

├── 1.2 Requirements

│   ├── 1.2.1 Business Requirements

│   ├── 1.2.2 Functional Requirements

│   └── 1.2.3 Non-functional Requirements

│

├── 1.3 UI/UX Design

│   ├── 1.3.1 Wireframes

│   ├── 1.3.2 UI Design

│   └── 1.3.3 Prototype

│

├── 1.4 Development

│   ├── 1.4.1 User Management

│   ├── 1.4.2 Product Management

│   ├── 1.4.3 Shopping Cart

│   ├── 1.4.4 Payment

│   └── 1.4.5 Order Management

│

├── 1.5 Testing

│   ├── 1.5.1 Functional Testing

│   ├── 1.5.2 Integration Testing

│   ├── 1.5.3 Performance Testing

│   └── 1.5.4 Security Testing

│

├── 1.6 Deployment

│

└── 1.7 Project Closure

WBS → Work Package

For example:

1.4.4 Payment

can be further broken into:

- Payment API integration

- Payment processing

- Payment failure handling

- Payment testing

The lowest manageable level is generally called a work package.

4. Project Estimation Techniques

Estimation means predicting:

- How much work?

- How long?

- How many resources?

- How much money?

Common techniques include:

| Technique | Mainly Used For | Example |
| --- | --- | --- |
| Analogous Estimation | Similar past projects | Previous project took 6 months |
| Parametric Estimation | Mathematical relationship | $100 × 1,000 units |
| Bottom-Up Estimation | Detailed work packages | Estimate each WBS item |
| Three-Point Estimation | Uncertainty | PERT |
| Expert Judgment | Expert experience | Senior developer estimate |
| Agile Estimation | Agile teams | Story points |

5. PERT Estimation

PERT = Program Evaluation and Review Technique

PERT uses three estimates:

- O = Optimistic

- M = Most Likely

- P = Pessimistic

Formula

Example

Suppose development may take:

- Optimistic = 4 days

- Most likely = 6 days

- Pessimistic = 10 days

Then:

So the estimated duration is approximately 6.3 days.

When to use?

PERT is useful when there is uncertainty in activity duration.

6. COCOMO Estimation

COCOMO = Constructive Cost Model

COCOMO is primarily used for estimating software development effort, cost and schedule based on software size, traditionally measured in KLOC (thousand lines of code).

Basic COCOMO Formula

Where:

- Effort = person-months

- KLOC = thousand lines of code

- a and b = model-specific constants

Example

Suppose:

Software size = 10 KLOC

For an organic project, using the basic COCOMO coefficients:

Approximately:

26.9 person-months

So the project may require around 27 person-months of effort.

COCOMO is useful for:

- Software effort estimation

- Cost estimation

- Schedule estimation

- Resource planning

7. Agile Estimation

Agile teams usually estimate relative complexity rather than exact hours.

The most common technique is Story Points.

Example

| User Story | Story Points |
| --- | --- |
| Login | 2 |
| User Registration | 3 |
| Product Search | 5 |
| Payment Integration | 8 |
| Recommendation Engine | 13 |

The larger the number, generally the greater the relative effort/complexity/uncertainty.

Planning Poker

Team members independently select story-point values:

Developer A → 5

Developer B → 8

Developer C → 5

Developer D → 8

They discuss differences and agree on:

5 or 8 points

Velocity

If a team delivers:

- Sprint 1 → 25 points

- Sprint 2 → 28 points

- Sprint 3 → 27 points

Average velocity:

Approximately 27 story points/sprint.

If the backlog has 135 points:

So approximately 5 sprints are required.

8. Developing Project Schedule

Once activities have been identified and estimated, we develop the project schedule.

Main steps

Define Activities

↓

Sequence Activities

↓

Estimate Resources

↓

Estimate Duration

↓

Develop Schedule

↓

Baseline Schedule

↓

Monitor & Control

9. Gantt Chart

A Gantt Chart is a visual representation of project activities against time.

Example

Project: E-Commerce Application

| Activity | W1 | W2 | W3 | W4 | W5 | W6 |
| --- | --- | --- | --- | --- | --- | --- |
| Requirements | ███ | ███ |  |  |  |  |
| UI/UX |  | ███ | ███ |  |  |  |
| Development |  |  | ███ | ███ | ███ |  |
| Testing |  |  |  |  | ███ | ███ |
| Deployment |  |  |  |  |  | ███ |

It helps the project manager see:

- Start date

- End date

- Duration

- Dependencies

- Progress

- Overlapping activities

10. Critical Path Method — CPM

CPM identifies the longest sequence of dependent activities in a project.

The critical path determines the shortest possible project duration.

Important rule

Activities on the critical path generally have zero total float.

If a critical activity is delayed by 2 days, the project can be delayed by approximately 2 days unless corrective action is taken.

Example

Suppose:

A: Requirements = 3 days

↓

B: Design = 4 days

↓

C: Development = 8 days

↓

D: Testing = 5 days

Total:

Critical Path:

A → B → C → D

Project duration = 20 days

Example with two paths

→ B (4) →

A (3)                D (5)

→ C (8) →

Path 1:

A → B → D

= 3 + 4 + 5

= 12 days

Path 2:

A → C → D

= 3 + 8 + 5

= 16 days

Therefore:

Critical Path = A → C → D

Project Duration = 16 days

11. Budgeting and Cost Management

Project Cost Management involves estimating, budgeting and controlling costs so that the project is completed within the approved budget.

Three major activities

Plan Cost Management

↓

Estimate Costs

↓

Determine Budget

↓

Control Costs

A. Estimate Costs

Estimate the cost of each activity/work package.

Example

| Work Package | Estimated Cost |
| --- | --- |
| Requirements | $5,000 |
| UI/UX | $8,000 |
| Development | $40,000 |
| Testing | $15,000 |
| Deployment | $7,000 |
| Project Management | $10,000 |
| Total | $85,000 |

B. Determine Budget

The individual estimates are aggregated to create the cost baseline.

Example:

Requirements       $5K

UI/UX               $8K

Development        $40K

Testing            $15K

Deployment          $7K

PM                 $10K

─────

Cost Baseline      $85K

An organization may also maintain a management reserve for unforeseen work within the project's overall funding requirements.

For example:

Cost Baseline = $85,000

Management Reserve = $5,000

Total Project Budget = $90,000

12. Cost Control Example

Suppose:

Budget = $100,000

After 3 months:

- Planned work = $60,000

- Actual cost = $70,000

The project has spent more than planned.

If the earned value (EV) is $60,000 and actual cost (AC) is $70,000:

Negative cost variance means:

The project is over budget.

13. Complete Example — IT Project

Project: Online Banking Application

| Planning Area | Example |
| --- | --- |
| Scope | Develop online banking application |
| Duration | 6 months |
| Budget | $500,000 |
| Team | PM, BA, Developers, QA, DevOps |
| WBS | Requirements → Design → Development → Testing → Deployment |
| Estimation | PERT + Expert Judgment + Agile Story Points |
| Schedule | Gantt Chart |
| Critical Path | Requirements → Development → Integration → Testing → Deployment |
| Cost Management | Cost estimates + Cost Baseline + Cost Control |
| Risks | Security issues, requirement changes, integration failure |
| Quality | Test coverage, defect targets, security testing |
| Stakeholders | Customer, Sponsor, Bank, Project Team |

Overall flow

PROJECT CHARTER

↓

PROJECT PLAN

↓

SCOPE

↓

WBS

↓

ACTIVITIES

↓

ESTIMATION

┌───────────┼───────────┐

↓           ↓           ↓

PERT       COCOMO      AGILE

↓           ↓        STORY POINTS

└───────────┼───────────┘

↓

PROJECT SCHEDULE

↓

GANTT + CRITICAL PATH

↓

COST ESTIMATION

↓

BUDGET

↓

BASELINES / PROJECT PLAN

↓

EXECUTION & CONTROL

Easy way to remember

WBS → WHAT?
What work needs to be done?

Estimation → HOW MUCH?
How much effort/time/cost?

Schedule → WHEN?
When will the work happen?

Gantt → SHOW WHEN
Visual timeline.

CPM → WHAT CAN DELAY US?
Find the critical path.

Budget → HOW MUCH MONEY?
How much will the project cost?

Cost Control → ARE WE WITHIN BUDGET?
Compare actual performance against the approved cost baseline.